# COMP507 IT Project Management — Assignment 1, Part 1

Project: PMS Comparison (Cloud-Based Project Management Software Review)

Team: Matthew Rushmer, Isaiah Thompson, Rahul Shankar, Bradley Ah Sam

Compiled documents: 1. Business Case  |  1.5 Exhibit A - Financial Analysis  |  2. Stakeholder Register  |  3. Stakeholder Management Strategy  |  4. Project Charter  |  5. Team Contract  |  6. Kick-off Meeting Minutes  |  8. Team Meeting Minutes  |  9. Risk Register (v1)  |  10. Issue Register (v1)  |  11. Milestone Report (v1)

# 1. Business Case

Source: Templates/1. business case.doc (verified 20 Aug 2026)

Date: 30/07/2026

Author: Matthew Rushmer, Isaiah Thompson, Rahul Shankar, Bradely Oh Sam

Project Name: PMS Comparison

## 1.0 Introduction / Background

ECMS's R&D course sits at the centre of AUT's push toward industry-based teaching - every graduating BCIS student has to go through it, so whatever project management tooling we point them at effectively becomes their first real exposure to professional PM practice. That alone makes the choice worth getting right. There's also a timing issue driving this. ECMS is already partway through moving its PMS provisioning from upfront licensing to a SaaS/ASP model. That's a good call cost-wise, but it doesn't mean much to students if nobody tells them which tools actually qualify or why. Roughly 500 students a year, split across two semesters, will need an answer to that question starting Semester 1, 2026.

## 2.0 Business Objective

Build a curated, evidence-backed Wiki comparing two cloud-based PMS options (Microsoft Project excluded) across all five PM process groups, live by 1 February 2026, within the $200,000 budget - so every Semester 1, 2026 R&D team has what they need to pick a tool without doing their own market research first.

## 3.0 Current Situation and Problem/Opportunity Statement

Right now there's no standardised PMS guidance, and the licensing change to per-user SaaS billing ($15/user/year) hasn't been communicated to students - leaving ~500 students a year to independently evaluate tools with no quality control or clear starting point. A single curated Wiki fixes that: it guides the full cohort toward suitable tools, lifts consistency in R&D project delivery, and - since enrolment holds steady through 2027 - keeps paying off across multiple cohorts without needing to be rebuilt each time.

## 4.0 Critical Assumption and Constraints

Assumptions

Existing ECMS IT infrastructure can already host the Wiki and support lab access to both PMS platforms, so no additional infrastructure spend is needed.

Enrolment (350 in Sem 1, 150 in Sem 2 - 500/year) and the $15/user/year PMS fee hold steady through 2027; only the internet charge is expected to rise, at 10% a year.

Constraints

The budget is capped at $200,000, and the schedule is fixed: planning begins 1 August 2025, implementation has to be done by 30 December 2025, and the Wiki needs to be live by 1 February 2026 - there's no room to slip past the Semester 1, 2026 start date.

On the content side, Microsoft Project can't be one of the two options, only two tools can be featured at all, and the whole write-up is capped at 4,500 words.

## 5.0 Analysis of Options and Recommendation

| Option | Description | Pros | Cons |
| --- | --- | --- | --- |
| A. Do nothing | Students find and choose their own PMS | No project cost | Inconsistent tool quality; duplicated research effort; doesn’t support the SaaS transition |
| B. Mandate a single PMS | ECMS picks one tool and requires everyone to use it | Straightforward to support | Removes student choice; creates a single point of failure if that tool falls short |
| C. Curated two-tool Wiki (recommended) | Evaluate the market against defined criteria, then document and compare two vetted tools across all five process groups | Balances guidance with genuine choice; fits within budget, timeline, and word-count limits; reusable across future cohorts | Needs dedicated evaluation and quality-review effort upfront |

Option C is the recommendation - it's the only one that actually satisfies all of the stated constraints while still moving the needle on the business objective.

## 6.0 Preliminary Project Requirements

Functional Requirements

Document the criteria used to shortlist candidate PMS tools.

Present a side-by-side comparison of the two selected tools, covering at least one key feature per PM process group (Initiating, Planning, Executing, Monitoring/Controlling, Closing).

Reference Microsoft Project's feature set as a benchmark for deriving comparison criteria, without listing it as a selectable option.

Support every comparative claim with a citation to a trusted public-domain or academic source.

Structure the content so it can be navigated by process group and by tool.

Allow ECMS staff to edit and update the content after initial publication.

Non-Functional Requirements

Availability: live and accessible by 1 February 2026, usable across each semester.

Accessibility: reachable from lab machines and remotely, on existing ECMS infrastructure - no new infrastructure required.

Quality: accurate, current, well-sourced content that meets ECMS's “very high quality” bar.

Usability: written and structured for a student audience, not PM specialists.

Compliance: total PMS content stays within the 4,500-word limit.

Maintainability: structured so it can be revised as tools or pricing change in later years.

## 7.0 Budget Estimate and Financial Analysis

The project is capped at the allocated $200,000, spent in Year 0 (2025) to build and launch the Wiki. The main ongoing cost after that is internet access for the ~500 students using the two PMS platforms in ECMS labs - $6/student/month in 2025, rising 10% a year through 2027. Set against that is the $1,200,000/year software-cost saving ECMS expects once R&D teams are actually on the SaaS PMS instead of buying licenses upfront, realised from Year 1 (2026) once the Wiki is live and guiding tool selection. We've treated the $1.2M saving as already net of the new $15/user SaaS fee. Using a 7% discount rate the project returns an NPV of ~$2.80M and an ROI of ~809% over the four-year analysis window, paying back the Year 0 cost within the first three months of Year 1. Full year-by-year workings are in Exhibit A.

## 8.0 Schedule Estimate

High-level milestones, per the brief's stated timeline:

Planning phase starts 1 August 2025

Implementation complete 30 December 2025

Wiki live 1 February 2026, ahead of Semester 1, 2026

These dates predate the real Semester 2, 2026 offering of this course, so we're using them as given and will confirm with the lecturer whether the whole timeline should shift forward a year. A detailed schedule baseline, network diagram, and critical path analysis follow in Part 2.

## 9.0 Potential Risks

| Risk | Category | Response |
| --- | --- | --- |
| Chosen PMS pricing or features change before go-live | Technology | Re-verify vendor pricing close to publish date |
| Wiki content exceeds the 4,500-word cap | Scope | Draft comparison tables early; track word count weekly |
| Sources aren't credible enough to support claims | Quality | Cite only vendor docs, academic journals, or established PM publications |
| Enrolment or fee figures change before Semester 1, 2026 | Cost | Re-verify against ECMS before final submission |
| A team member is unavailable and a section slips | Resource | Team contract + weekly check-ins (see Team Contract) |

## 10.0 Exhibits

Exhibit A: Financial Analysis — see section 1.5, immediately following this document, for the full table.

# 1.5. Exhibit A — Financial Analysis

Source: Templates/1.5. Exhibit A - Financial Analysis.csv (verified 20 Aug 2026)

| Metric | Year 0 (2025) | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | Total |
| --- | --- | --- | --- | --- | --- |
| Costs | 236,000.00 | 39,600.00 | 43,560.00 | 43,560.00 |  |
| Discount factor | 1.0000 | 0.9346 | 0.8734 | 0.8163 |  |
| Discounted costs | 236,000.00 | 37,009.35 | 38,046.99 | 35,557.94 | 346,614.27 |
| Benefits | 0.00 | 1,200,000.00 | 1,200,000.00 | 1,200,000.00 |  |
| Discount factor | 1.0000 | 0.9346 | 0.8734 | 0.8163 |  |
| Discounted benefits | 0.00 | 1,121,495.33 | 1,048,126.47 | 979,557.45 | 3,149,179.25 |
| Discounted benefits - costs (NPV) | (236,000.00) | 1,084,485.98 | 1,010,079.48 | 943,999.52 | 2,802,564.98 |
| Cumulative | (236,000.00) | 848,485.98 | 1,858,565.46 | 2,802,564.98 |  |

Discount rate: 7%   |   ROI: 808.6%   |   Payback: Year 1 (~2.6 months in)

# 2. Stakeholder Register

Source: Templates/2. stakeholder register-finished.docx (verified 20 Aug 2026)

Stakeholder Register

Author: Mathew, Isaiah, Rahul, Bradley

Date:30/07/26

Project Name: PMS Comparison

| Name | Position | Internal/External | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| Mathew | Project Manager | Internal | Coordinates the project, assigns tasks, monitors progress | ftc7312@autuni.ac.nz |
| Isaiah | Project member | Internal | Conducts research and contributes to the report | kgb2156@autuni.ac.nz |
| Rahul | Project member | Internal | Assists with research, documentation and presentation | gpg6703@autuni.ac.nz |
| Bradley | Project member | Internal | Assists with analysis, editing and quality checking | fss2720@autuni.ac.nz |
| Manpreet Dhanjal | Project Supervisor | External | Provides groups/feedback and assesses the project | manpreet.kaur.dhanjal@aut.ac.nz |

# 3. Stakeholder Management Strategy

Source: Templates/3. stakeholder management strategy.doc (verified 20 Aug 2026)

| Name | Level of Interest | Level of Influence | Potential Management Strategies |
| --- | --- | --- | --- |
| ECMS Program Sponsor | High | High | Manage closely - fortnightly status updates, sign-off required at each milestone report (v1/v2); involve in setting the PMS selection criteria early so there are no surprises at review. |
| Project Team (Matthew, Isaiah, Rahul, Bradley) | High | High | Manage closely - weekly team meetings with agenda and minutes, RACI and roles fixed in the Team Contract and Project Charter, shared task tracker so interest and effort stay aligned. |
| R&D Course Coordinator | High | Medium-High | Manage closely - involve early in defining the evaluation criteria for the two PMS, since they'll assess R&D teams against the same standard; review the draft Wiki before it goes live. |
| R&D Students (Sem 1 and Sem 2 intake) | High | Low | Keep informed - no formal decision role, but the whole project exists for them; short intro/FAQ on the Wiki itself plus a launch announcement, and an informal feedback channel post-launch. |
| ECMS IT/Infrastructure Support | Medium | Medium | Keep satisfied - confirm early that current infrastructure covers Wiki hosting and lab access (per the business case assumption); loop in only at go-live or if a hosting issue comes up. |
| Selected SaaS PMS Vendors | Low | Low | Monitor - no direct engagement needed; check their public pricing/feature pages periodically before publish date in case anything changes. |

# 4. Project Charter incl. Roles & Responsibilities

Source: Templates/4. Project Charter-final.docx (verified 20 Aug 2026)

Project Charter

Author: Isaiah, Matthew, Bradley, Rahul

Date: 07/30/26

Project Title: 	PMS Comparison

Project Start Date:  07/30/26                    Projected Finish Date: 08/23/26

Budget Information: $200,000 NZD preliminary

Project Manager: Matthew Rushmer, 022 087 9529, ftc7312@autuni.ac.nz

Project Objectives:

Develop a wiki project that will compare two different wikis fit for the R&D students.

Success Criteria:

The wiki word count must be below 4500.

The project must not exceed the preliminary budget.

The wiki must be completely finished before the project finish date.

The wiki must be easy to read and informative to the R&D students.

Approach:

Planning- The team will fill out 11 different documents including but not limited to a project charter, a business case, a stockholder strategy paper, and a financial analysis to make a proper plan.

Designing- The team will make the wiki project in accordance with the planning done.

Review – Throughout the entire project, we will periodically hold review sessions to make sure we remain in the budget, scope, and objective of the project.

Feedback collection- The team will collect a sample group of current and former R&D students to give their thoughts on the wiki. We will then use that feedback to go back into the planning stage. Repeat until satisfactory.

Delivery- The wiki site will be installed into the schools servers becoming public. The teachers of R&D will spread the link to the website to the R&D students.

Procedure for change request:

Email the project manager with change request.

If the change is approved by the project manager, the above stakeholders will be immediately notified.

The team will change the relevant planning documents immediately.

If relevant, the design of the wiki project will be altered to reflect the changes in the relevant changes in the planning documents.

Issue management process:

If there is an issue is not immediately fixable, email the issue manager(currently Bradley).

The issue will be logged by the issue manager in the issue manager excel sheet with all relevant info.

The issue manager will also email the relevant worker to notify them of the issue as well as the project manager.

When fixed, the issue will be status will be set as resolved and the solution will be put in the comments section.

Roles and Responsibilities

| Name and Signature | Role | Position | Contact Information |
| --- | --- | --- | --- |
| Matthew Rushmer | Ensures team stays on track | Team Lead | ftc7312@autuni.ac.nz |
| Isaiah Thompson | Anylyzes the risks to better inform the team | Risk analyzer | kgb2156@autuni.ac.nz |
| Bradley Ah Sam | Keeps track of all the issues | Issue manager | fss2720@autuni.ac.nz |
| Rahul Shankar | Informs and advocates for the stakeholders | Stakeholder advisor | gpg6703@autuni.ac.nz |

Comments: (Handwritten or typed comments from above stakeholders, if applicable)

# 5. Team Contract

Source: Templates/5. Team Contract-final.docx (verified 20 Aug 2026)

Team Contract

Author: Mathew, Isaiah, Rahul,

Date: 30/07/26

Version: 1.2

Project Name: PMS Comparison

Project Team Members’ Names and Sign-off:

| Name | Date |
| --- | --- |
| Mathew | 23/07/2026 |
| Isaiah | 23/07/2026 |
| Rahul | 23/07/2026 |
| Bradley | 23/07/2026 |

Code of Conduct:  As a project team, we will:

Complete our assigned tasks on time

Contribute fairly to the project

Treat all team members with respect

Participation: We will:

Attend all team meeting

Help team members if they need assistance

Take responsibility and control of our own assigned tasks

Communication: We will:

Communicate professionally and respectfully at all times

Respond to team messages within 24 hours.

Inform team members of our individual  progress throughout the project and assigned tasks

Problem Solving: We will:

Discuss and resolve disagreements throughout the project respectfully

Listening to everyone’s inputs and ideas before making the decision.

Ask lecturer or TA for guidance if we cannot solve an issue ourselves

Meeting Guidelines: We will:

Arrive on time for meetings

Stay focused on the meeting agenda during team meetings.

Record details of the meetings, such as date, reason and members present

# 6. Kick-off Meeting Agenda & Minutes

Source: Templates/6. kick-off-meeting-final.docx (verified 20 Aug 2026)

Kick-Off Meeting

Author: Isaiah, Matthew, Bradley, Rahul

Date: 07/30/2026

Project Name: PMS Comparison

Meeting Objective:

Get started with the preparing phase of the project by reviewing the objective and important paperwork. Assign paperwork to the team members.

Agenda:

Took attendance. Rahul was late because of car troubles, and Bradley couldn’t come today.

Exchanged contact information.

Reviewed the objective including scope, time, and cost goals.

Matthew assigned project related documents. We will be assigned  more fixed roles next meeting.

Concluded the meeting.

used the rest of our time to work and discuss project related documents.

List of action items from the meeting is below.

| Action Item | Assigned To | Due Date |
| --- | --- | --- |
| Business case | Matthew Rushmer | 05/08/26 |
| Stakeholder management strategy | Matthew Rushmer | 12/08/26 |
| Client meeting agenda/minutes | Matthew Rushmer | Ongoing |
| Project charter | Isaiah Thompson | 08/08/26 |
| Kick off meeting agenda/minutes | Isaiah Thompson | 07/30/26 |
| Risk register | Isaiah Thompson | Ongoing |
| Stakeholder Register | Rahul Shankar | 08/05/26 |
| Team contract | Rahul Shankar | 08/05/26 |
| Next team meeting agenda/minutes | Rahul Shankar | 08/05/26 |
| Issue register | Bradley | Ongoing |
| Milestone Report | Bradley | Ongoing |

Date and time of next meeting: 08/06/26

# 7. Client Meeting Agenda & Minutes

Source: Templates/7. Client Meeting_Template-final.docx (verified 22 Aug 2026)

## Client Meeting 1 — Thursday 23 July 2026

Client/Project: PMS Comparison

Purpose: Kickoff follow-up: confirm weekly check-in structure and PMS shortlisting approach

Meeting called by: Matthew Rushmer

Location: WS Building   |   Date: 23/07/2026   |   Time: 9:30am

QA:   |   Version:   |   Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| None recorded |  |

Minutes prepared by: Matthew

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Confirm expectations for weekly check-ins with the TA | Matthew | 10 min |
| 2 | Review team roles from the Project Charter | Isaiah | 10 min |
| 3 | Agree criteria for shortlisting the two PMS candidates | Rahul | 15 min |
| 4 | Q&A / next steps | All | 10 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| None (first meeting) | None (first meeting) | None (first meeting) | None (first meeting) |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Matthew confirmed the weekly Thursday check-in slot with Manpreet as the ongoing TA/client contact. |
| 2 | No project documents had been produced yet, so the discussion stayed high-level: expectations for the weekly check-ins. |
| 3 | Agreed to formally assign roles and paperwork once the whole team could meet at the internal kickoff. |
| 4 | Rahul and Bradley agreed to start informal PMS candidate research ahead of that kickoff rather than waiting. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Book and hold the internal team kickoff | Matthew | 30/07/26 |
| 2 | Start informal PMS candidate research ahead of kickoff | Rahul & Bradley | 30/07/26 |
| 3 | Confirm full team availability for the weekly Thursday slot | All | 30/07/26 |

Next Meeting

Date: 30 July 2026 | Time: 9:30am

Discussion points for the next meeting:

• Review roles and paperwork assignments made at kickoff

• Confirm progress on PMS candidate research

• Discuss the business case draft status

Action Items to be discussed in the next meeting:

• Confirm role assignments from kickoff

• Report initial PMS research findings

• Agree next steps on the business case draft

TA Feedback (Week 1)

Good first check. One note: don't let “PMS shortlisting” stay informal for two weeks running. Walk into the kickoff with at least a rough candidate list, even an imperfect one, so that meeting produces a decision instead of just another to-do.

## Client Meeting 2 — Thursday 30 July 2026

Client/Project: PMS Comparison

Purpose: Progress check: PMS shortlisting and business case draft

Meeting called by: Matthew Rushmer

Location: WS Building   |   Date: 30/07/2026   |   Time: 9:30am

QA:   |   Version:   |   Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Bradley Ah Sam | Issue Manager |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Update on narrowing the two PMS candidates | Rahul | 10 min |
| 2 | Any blockers on research so far | All | 10 min |
| 3 | Business case draft status | Matthew | 15 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Book and hold the internal team kickoff | Matthew | Closed — held today |
| 2 | Start informal PMS candidate research ahead of kickoff | Rahul & Bradley | Closed — underway |
| 3 | Confirm full team availability for the weekly Thursday slot | All | Closed — confirmed |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | This week's meeting doubled as the internal team kickoff. |
| 2 | Reviewed the Assignment 1 Part 1 brief and marking criteria, and exchanged contact details. |
| 3 | Matthew was confirmed as project leader. |
| 4 | Documents were assigned: Matthew — Business Case, Stakeholder Management Strategy, Client Meeting Minutes; Isaiah — Project Charter, Kick-off Minutes, Risk Register; Rahul — Stakeholder Register, Team Contract, Team Meeting Minutes; Bradley — Issue Register, Milestone Report (assigned in his absence, to be briefed). |
| 5 | Bradley could not attend, and Rahul was separately delayed by car trouble. |
| 6 | The business case draft itself hadn't started yet — today's session was about ownership, not content. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Business Case | Matthew | 05/08/26 |
| 2 | Stakeholder Management Strategy | Matthew | 12/08/26 |
| 3 | Project Charter | Isaiah | 08/08/26 |
| 4 | Risk Register | Isaiah | Ongoing |
| 5 | Stakeholder Register & Team Contract | Rahul | 05/08/26 |
| 6 | Issue Register & Milestone Report (pending Bradley being briefed) | Bradley | Ongoing |

Next Meeting

Date: 6 August 2026 | Time: 9:43am

Discussion points for the next meeting:

• Update on stakeholder register / management strategy progress

• Confirm the two PMS finalists

• Check scope and word-count tracking against the 4,500-word cap

Action Items to be discussed in the next meeting:

• Confirm PMS finalists

• Provide progress update on the business case and stakeholder documents

• Flag any blockers before next week

TA Feedback (Week 2)

Clear ownership across the whole document list is exactly what I want to see. Two things to note: Bradley missed the meeting and picked up the two documents with the least explanation behind them, so make sure someone briefs him properly before he's expected to produce anything, or you'll be redoing that work in week 3. Also, “ongoing” isn't a due date, put an actual date on the Risk Register next time.

## Client Meeting 3 — Thursday 6 August 2026

Client/Project: PMS Comparison

Purpose: Stakeholder documents progress; confirm PMS finalists

Meeting called by: Rahul Shankar

Location: WS Building   |   Date: 06/08/2026   |   Time: 9:43am

QA:   |   Version:   |   Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Stakeholder register / management strategy progress | Isaiah | 10 min |
| 2 | Confirm the two PMS finalists | Rahul / Bradley | 15 min |
| 3 | Check scope and word-count tracking against the 4,500-word cap | Matthew | 10 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Business Case | Matthew | In progress |
| 2 | Stakeholder Management Strategy | Matthew | In progress |
| 3 | Project Charter | Isaiah | In progress |
| 4 | Risk Register | Isaiah | Ongoing |
| 5 | Stakeholder Register & Team Contract | Rahul | In progress |
| 6 | Issue Register & Milestone Report | Bradley | Pending briefing |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Most of this session went into catching Bradley up rather than the planned PMS-finalist discussion. |
| 2 | Rahul walked Bradley through what was agreed at kickoff and explained the Issue Register and Milestone Report in detail. |
| 3 | Bradley was shown the expected due dates and how the documents should be completed, and asked clarifying questions. |
| 4 | Because the handover took priority, the two PMS finalists weren't formally confirmed this week. |
| 5 | Rahul and Bradley agreed to lock in the PMS finalists once Bradley's onboarding was complete. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | 13/08/26 |
| 2 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Update Matthew and Isaiah on Bradley's progress | Rahul | 13/08/26 |
| 5 | Confirm PMS finalists (carried over, now overdue) | Rahul & Bradley | 13/08/26 |

Next Meeting

Date: 13 August 2026 | Time: 9:21am

Discussion points for the next meeting:

• Business case financials review (NPV / ROI / payback)

• Risk register v1 status

• Outstanding items before Part 1 submission

Action Items to be discussed in the next meeting:

• Finalise PMS finalist confirmation

• Review business case financials

• Identify any remaining outstanding work

TA Feedback (Week 3)

You spent your team-meeting time re-explaining the project to someone who missed kickoff instead of doing the PMS-finalist work you told me you'd have done  that's not a Bradley problem, it's a handover problem. A short briefing note sent the day after kickoff would have saved this whole session. Get the finalists locked in before next week; it's now overdue.

## Client Meeting 4 — Thursday 13 August 2026

Client/Project: PMS Comparison

Purpose: Business case financials and risk register review

Meeting called by: Matthew Rushmer

Location: WS Buidling   |   Date: 13/08/2026   |   Time: 9:21am

QA:   |   Version:   |   Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Business case financials review (NPV / ROI / payback) | Matthew | 15 min |
| 2 | Risk register v1 status | Isaiah | 10 min |
| 3 | Outstanding items before Part 1 submission | All | 10 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | Done — first draft presented |
| 2 | Prepare first draft of Milestone Report | Bradley | Done |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | In progress |
| 4 | Confirm PMS finalists | Rahul & Bradley | Confirmed |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | All members reported progress: Business Case, Stakeholder Register and Team Contract are underway. |
| 2 | Isaiah gave a Risk Register update. |
| 3 | Bradley presented first drafts of the Issue Register and Milestone Report, confirming he understood his responsibilities after last week's briefing. |
| 4 | The team flagged several documents still needing proofreading and formatting. |
| 5 | The final team meeting was scheduled for 20 August. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy | Matthew | 20/08/26 |
| 2 | Update Project Charter and Risk Register | Isaiah | 20/08/26 |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | 20/08/26 |
| 4 | Finalise Issue Register and Milestone Report | Bradley | 20/08/26 |
| 5 | Proofread assigned documents before final meeting | All | 20/08/26 |

Next Meeting

Date: 20 August 2026 | Time: 9:15am

Discussion points for the next meeting:

• Part 1 completion status review (all 11 items)

• Outstanding items: Issue Register v1, Milestone Report v1

• Submission logistics and final checks

Action Items to be discussed in the next meeting:

• Confirm all 11 items are complete

• Resolve any remaining incomplete work

• Confirm submission responsibilities

TA Feedback (Week 4)

With a week left, the Business Case financials and the Risk Register are the two I'd watch: financial errors are the easiest thing for a marker to catch, so get a second pair of eyes on the NPV/ROI/payback numbers before Wednesday, not Friday night.

## Client Meeting 5 — Thursday 20 August 2026

Client/Project: PMS Comparison

Purpose: Final Part 1 readiness check

Meeting called by: Matthew Rushmer

Location: WS Building   |   Date: 20/08/2026   |   Time: 9:15am

QA:   |   Version:   |   Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| None recorded |  |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Part 1 completion status review (all 11 items) | Matthew | 10 min |
| 2 | Outstanding items: Issue Register v1, Milestone Report v1 | Bradley | 10 min |
| 3 | Submission logistics and final checks | All | 10 min |
| 4 | Next steps into Part 2 | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy | Matthew | Due today |
| 2 | Update Project Charter and Risk Register | Isaiah | Due today |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | Due today |
| 4 | Finalise Issue Register and Milestone Report | Bradley | Due today |
| 5 | Proofread assigned documents | All | Due today |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | The team reviewed completion status across all 11 Part 1 items. |
| 2 | Updated the Risk Register and Issue Register where required. |
| 3 | Checked that document formatting and terminology were consistent across the pack. |
| 4 | A handful of minor spelling, formatting and wording issues were identified for correction. |
| 5 | Outstanding sections were assigned back to their owners for same-day fixes. |
| 6 | The team confirmed everything would be ready ahead of the 23 August deadline, with Matthew performing the final check before submission. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete final check of Business Case and full document set | Matthew | 22/08/26 |
| 2 | Complete final update of Risk Register | Isaiah | 22/08/26 |
| 3 | Complete and organise all team meeting documentation | Rahul | 22/08/26 |
| 4 | Complete final Issue Register and Milestone Report | Bradley | 22/08/26 |
| 5 | Review final project pack before submission | All | 22/08/26 |

Next Meeting

Date: needs to be set | Time: N/A — Part 1 submitted

Discussion points for the next meeting:

• Part 2 planning

• Carry forward learnings from Part 1

Action Items to be discussed in the next meeting:

• Confirm Part 2 timeline once released

TA Feedback (Week 5)

Two things before you submit: double-check Issue #1 in the register, its due date currently sits before the project start date, which is the kind of small error that reads as carelessness to a marker even though the substance is fine. And make sure these Client Meeting Minutes actually get attached. it's the item I most often see teams forget in the rush to submit everything else.

# 8. Team Meeting Agenda & Minutes

Source: Templates/8. Meeting_Minutes_Template_redo-final.docx (verified 21 Aug 2026)

.

## Team Meeting 1 — 06/08/26

Purpose: Continue working on assigned tasks and discuss any issues we may have about our assigned tasks.

Meeting called by: Mathew (Project Leader)

Location: AUT – WS220   |   Date: 06/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew   |   Version: 1.0   |   Minutes Reviewed By: Rahul

Attendees

| Name | Representing |
| --- | --- |
| Rahul |  |
| Bradley |  |

Absent

| Name | Representing |
| --- | --- |
| Isaiah | Project Member |
| Mathew | Project Leader |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Update Bradley on the project | Rahul | 10 minutes |
| 2 | Explain Bradley’s assigned tasks | Rahul | 10 minutes |
| 3 | Discuss due dates and expectations | Rahul | 15 minutes |
| 4 | Explain how to complete the Issue Register and Milestone Report | Rahul | 10 minutes |
| 5 | Discuss next steps and questions | Rahul | 15 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete Business Case and related documents | Mathew | Ongoing |
| 2 | Complete Project Charter and Risk Register | Isaiah | Ongoing |
| 3 | Complete Stakeholder Register and Team Contract | Rahul | Ongoing |
| 4 | Complete Issue Register | Bradley | Ongoing |
| 5 | Complete Milestone Report | Bradley | TBA |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Rahul updated Bradley on what had been discussed during the kick-off meeting. |
| 2 | Bradley was informed of the overall project requirements and submission deadline. |
| 3 | Rahul explained that Bradley had been assigned the Issue Register and Milestone Report. |
| 4 | The purpose and structure of the Issue Register were explained. |
| 5 | The purpose and structure of the Milestone Report were explained. |
| 6 | Bradley was shown the expected due dates and how the documents should be completed. |
| 7 | Bradley asked questions about his assigned tasks and clarified what was required. |
| 8 | Bradley agreed to begin working on his assigned documents before the next meeting. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | 13/08/26 |
| 2 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Update Mathew and Isaiah on Bradley’s progress | Rahul | 13/08/26 |
| 5 | Review progress at next meeting | Rahul & Bradley | 13/08/26 |

Next Meeting

Date: 13/08/26 | Time: 8:00 AM – 10:00 AM

Discussion points for the next meeting:

Review Bradley’s progress on the Issue Register and Milestone Report.

Review progress on other project documents.

Discuss any issues or changes needed before submission.

Action Items to be discussed in the next meeting:

Check whether assigned tasks are on schedule.

Identify outstanding work.

Plan the remaining work before the 23 August deadline.

## Team Meeting 2 — 13/08/26

Purpose: Review progress on assigned documents, discuss outstanding work, and prepare for the final stage of the project.

Meeting called by: Mathew(Project Leader)

Location: AUT – WS220   |   Date: 13/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew   |   Version: 1.0   |   Minutes Reviewed By: Mathew

Attendees

| Name | Representing |
| --- | --- |
| Mathew | Project leader |
| Isaiah | Project member |
| Bradley | Project member |
| Rahul | Project member |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Review progress on assigned project documents | All members | 20 minutes |
| 2 | Review Bradley's Issue Register and Milestone Report progress | Bradley | 15 minutes |
| 3 | Discuss risks, issues and incomplete work | All members | 10 minutes |
| 4 | Identify changes required before submission | Mathew | 15 minutes |
| 5 | Plan final week of project work | All members | 15 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete Business Case and related documents | Mathew | 13/08/26 |
| 2 | Complete Project Charter and update Risk Register | Isaiah | 13/08/26 ongoing |
| 3 | Complete Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Prepare Issue Register | Bradley | 13/08/26 |
| 5 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | All members provided an update on the progress of their assigned documents. |
| 2 | Bradley confirmed that he understood his responsibilities after being briefed at the previous meeting. |
| 3 | The team reviewed progress on the Business Case, Project Charter, Stakeholder Register and Team Contract. |
| 4 | Bradley presented progress on the Issue Register and Milestone Report. |
| 5 | Isaiah provided an update on risks identified in the Risk Register. |
| 6 | The team identified several documents that required final proofreading and formatting. |
| 7 | Members agreed to complete outstanding work before the final team meeting. |
| 8 | The final team meeting was scheduled for 20 August 2026. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy | Mathew | 20/08/26 |
| 2 | Update Project Charter and Risk Register | Isaiah | 20/08/26 |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | 20/08/26 |
| 4 | Finalise Issue Register and Milestone Report | Bradley | 20/08/26 |
| 5 | Proofread assigned documents before final meeting | All members | 20/08/26 |

Next Meeting

Date: 20/08/26 | Time: 8:00 AM – 10:00 AM

Discussion points for the next meeting:

Review all completed Part 1 documents.

Check formatting, accuracy and consistency.

Confirm everything is ready for submission.

Action Items to be discussed in the next meeting:

Resolve any remaining incomplete work.

Complete final proofreading.

Confirm submission responsibilities.

## Team Meeting 3 — 20/08/26

Purpose: Conduct a final review of Assignment 1 Part 1 documents and prepare the project for submission.

Meeting called by: Mathew (Project Leader)

Location: AUT – WS220   |   Date: 20/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew   |   Version: 1.0   |   Minutes Reviewed By: Mathew

Attendees

| Name | Representing |
| --- | --- |
| Mathew | Project leader |
| Isaiah | Project member |
| Bradley | Project member |
| Rahul | Project member |

Minutes prepared by: Rahul

Minutes circulation to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Review completion status of all Part 1 documents | Mathew | 20 minutes |
| 2 | Review risk and issue registers | Isaiah & Bradley | 15 minutes |
| 3 | Proofread and check document consistency | All members | 10 minutes |
| 4 | Identify and correct final issues | All members | 15 minutes |
| 5 | Confirm submission plan and responsibilities | Mathew | 10 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy |  |  |
| 2 | Update Project Charter and Risk Register |  |  |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation |  |  |
| 4 | Finalise Issue Register and Milestone Report |  |  |
| 5 | Proofread assigned project documents |  |  |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | The team reviewed the status of all documents required for Assignment 1 Part 1. |
| 2 | Each member confirmed the completion status of their assigned work. |
| 3 | The Risk Register and Issue Register were reviewed and updated where required. |
| 4 | The team checked that document formatting and terminology were consistent. |
| 5 | Minor spelling, formatting and wording issues were identified for correction. |
| 6 | Outstanding sections were assigned to the responsible team member for final completion. |
| 7 | The team confirmed that all documents would be completed before the 23 August deadline. |
| 8 | Mathew would perform the final check before submission. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete final check of Business Case and project documents | Mathew | 22/08/26 |
| 2 | Complete final update of Risk Register | Isaiah | 22/08/26 |
| 3 | Complete and organise all team meeting documentation | Rahul | 22/08/26 |
| 4 | Complete final Issue Register and Milestone Report | Bradley | 22/08/26 |
| 5 | Review final Project Wiki before submission | All members | 22/08/26 |

Next Meeting

Date: 23/08/26 | Time: 11:30 PM

Discussion points for the next meeting:

Final submission check.

Confirm all required documents have been included.

Confirm successful submission of Assignment 1 Part 1.

Action Items to be discussed in the next meeting:

Verify no required files are missing.

Confirm final version is ready.

Submit Assignment 1 Part 1.

# 9. Risk Register (v1)

Source: Templates/9. risk register version 1-final.xlsx (verified 20 Aug 2026)

| ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | Stakeholder confusion | Stakeholders confused and not informed about the project | Third-Party risk | Not planning with stakeholders in mind | Lack of stakeholder meetings | Set up a meeting with stakeholders to discuss progress. | Rahul Shankar | 4 | 3 | closed |
| 2 | 5 | Above word count | Wiki page above the 4500 word limit. | Scope risk | Not writing with scope in mind | Lack of conciseness, over bloated wording. | Proof read to make sure everything is essential and brief | Matthew Rushmer | 2 | 4 | open |
| 3 | 1 | Above budget | Going above the 200,000$ budget for the wiki page | Financial Risk | Lavish spending | Lack of proper financial spending and plan | Keep Financial documents updated with budget in mind and go over spending during meetings | Matthew Rushmer | 1 | 5 | closed |
| 4 | 3 | Project due date | Delivering the wiki page past the given date. | Schedule Risk | Not enough work hours | Lack of workers. Poor management of current workers | Higher more people. Start assigning more hours to current workers. | Matthew Rushmer | 3 | 5 | open |
| 5 | 4 | Offline servers | Server outages preventing the users from accessing the site | Operational Risk | unreliable server. | Lack of backup servers. | Setup multiple hosts for the wiki page. | Bradley Ah Sam | 3 | 4 | open |

# 10. Issue Register (v1)

Source: Templates/10 issue log version 1.xls (verified 21 Aug 2026)

| Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hard to find good PMS information | May delay research | Week 2 | Bradley Ah Sam | Team Leader | M | 10/08/26 | Open | N/A |
| 2 | Team members have different schedules | May delay meeting | Week 5 | Bradley Ah Sam | Team Leader | L | 20/08/26 | Open | N/A |
| 3 | Team roles are unclear | Work may be missed | Week 1-2 | Bradley Ah Sam | Entire Team | M | 28/07/26 | Open | N/A |
| 4 | Some tasks may be late | Might delay Part 1 | Week 5-6 | Bradley Ah Sam | Entire Team | H | 23/08/26 | Open | N/A |

# 11. Milestone Report (v1)

Source: Templates/11. milestone report.doc (verified 21 Aug 2026)

Author: Bradley Ah Sam

Date: 07/08/26

| Milestone | Timeframe | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| Project team formed | Week 1 | Completed | Entire team |  |
| Roles and responsibilities assigned | Week 1-2 | Completed | Entire team |  |
| Kick off meeting | Week 1-2 | Completed | Mathew Rushmer |  |
| Business case | Week 3 | Completed | Mathew Rushmer |  |
| Stakeholder register | Week 3-4 | Completed | Rahul Shankar |  |
| Stakeholder management strategy completed | Week 3 | Completed | Mathew Rushmer |  |
| Project charter | Week 5 | Completed | Entire Team |  |
| Team contract signed | Week 4-5 | Completed | Entire Team |  |
| Risk register (Version 1) | Week 4 | Completed | Isaiah Thompson |  |
| Issue register (Version 1) | Week 6 | Completed | Bradley Ah Sam |  |
| Team meetings | Week 6 | Ongoing | Entire Team | Scheduling a time for all team members |
| Milestone report (Version 1) | Week 6 | Completed | Bradley Ah Sam |  |
| Part 1 ready for submission | Week 6 | Upcoming | Entire Team |  |