Team ASSIGNMENT COVERSHEET

ITPM (COMP507) Assignment 1 Part 1

|  | Lab Time: W203A | Lab TA: Manpreet Dhanjal |
| --- | --- | --- |
| Student ID 1.25288226 2. 25285879 3. 21142315 4. 26345265 | First Name Matthew Isaiah Rahul Bradley | Surname Rushmer Thompson Shankar Ah Sam |
| Team Name: BRIM |  |  |
| TA names: Manpreet Dhanjal |  |  |

Please read the following and place an X next to each statement to indicate your understanding:

| It is my team’s responsibility to keep a copy of the assignment. | X |
| --- | --- |
| The team has signed and read the Student Statement below. | X |
| The team understands that a software program (Turnitin) that detects plagiarism and copying may be used on my assignment. | X |

Plagiarism and Dishonesty are methods of cheating for the purposes of General Academic Regulations (GAR) http://www.aut.ac.nz/students/regulations.htm

Student’s Statement: This assessment is entirely our team’s work and has not been submitted in any other course of study. The team will submit a copy of this assessment to Turnitin if required. In this assessment, the team has acknowledged that to the best of the team’s ability:

- The source of direct quotes from the work of others

- The ideas of others (includes work from private or professional services, past assessments, other students, books, journals, cut/paste from internet sites and/or other materials)

- The source of diagrams

Signature:

- Matthew                             Date: 22/06/2026

- Isaiah                                  Date: 22/06/2026

- Rahul                                  Date: 22/06/2026

- Bradley                               Date: 22/06/2026

The information on this form is collected for the primary purpose of submitting your assignment for assessment. Other purposes of collection include receiving your acknowledgment of plagiarism policies and attending to administrative matters. If you choose not to complete all questions on this form, it may not be possible for the Faculty of Design and Creative Technologies to accept your assignment.

# 1. Business Case

Source: Templates/1. business case.doc (checked on 20 Aug 2026)

Date: 30/07/2026

Authors: Matthew Rushmer, Isaiah Thompson, Rahul Shankar, Bradley Ah Sam

Project Name: PMS Comparison

## 1.0 Introduction / Background

The development of ECMS' Research & Development class is the heart of AUT's industry-based teaching policy - all graduating BCIS students need to complete it. That alone is a reason for picking a proper PM tool. There is another reason - timing. The PMS provisioning of ECMS has been partly switched to a SaaS/ASP model for quite some time already. It is definitely a right decision from the financial perspective, yet the same cannot be said about students as they have no idea which PMSs would be qualified for use and why. Some 500 students per semester (or around 1,000 per year) would require this information starting the Semester 1, 2026.

## 2.0 Business Objective

Create a curating and evidence-based Wiki that compares two different cloud-based PMSs (Microsoft Project is not eligible) across all five process groups in PM, launched by 1 February 2026, with the budget of $200,000 - so every semester's R&D teams could select a proper tool without conducting additional market research themselves.

## 3.0 Current Situation and Problem/Opportunity Statement

There is no uniform guidance regarding PM tool selection, not to mention the change in licensing from the initial model to the SaaS/ASP model that charges per user ($15/user/year). This lack of communication leaves some 500 students to make a decision on their own. Such a Wiki could solve this problem as it would guide the whole cohort towards the proper PMSs, increase the consistency in completing R&D projects and, being created once, could benefit several cohorts in a row (as the enrolment is stable till 2027).

## 4.0 Critical Assumption and Constraints

Assumptions

Current ECMS' IT infrastructure is ready to host the Wiki and to provide lab access to both PMSs. No investment in new infrastructure is required.

Enrolment (350 in Sem 1, 150 in Sem 2 – 500/year) and $15/user/year PMS licence remain the same till 2027; only the internet cost increases every year by 10%.

Constraints

The budget is constrained by $200,000; similarly, the time constraint includes initiation of planning on 1 August 2025, completion of implementation by 30 December 2025, and making the Wiki operational by 1 February 2026 – there is no space left for delaying past the beginning of the Semester 1, 2026.

In terms of the content constraint, Microsoft Project cannot be one of the two tools selected, and only two tools can be included in the report at all. The entire content of the report is limited to 4,500 words.

## 5.0 Analysis of Options and Recommendation

| Option | Description | Pros | Cons |
| --- | --- | --- | --- |
| A. Do nothing | Students find and choose their own PMS | No project cost | Inconsistent tool quality; duplicated research effort; doesn’t support the SaaS transition |
| B. Mandate a single PMS | ECMS picks one tool and requires everyone to use it | Straightforward to support | Removes student choice; creates a single point of failure if that tool falls short |
| C. Curated two-tool Wiki (recommended) | Evaluate the market against defined criteria, then document and compare two vetted tools across all five process groups | Balances guidance with genuine choice; fits within budget, timeline, and word-count limits; reusable across future cohorts | Needs dedicated evaluation and quality-review effort upfront |

Option C is recommended because it is the only solution among the three options that complies with all the constraints imposed upon the project, while making some progress toward the business goal.

## 6.0 Preliminary Project Requirements

Functional Requirements

Explain the criteria used for the shortlisting of PMS tools under consideration.

Prepare a comparative analysis table that will contain at least one major function associated with each of the PM process groups (Initiating, Planning, Executing, Monitoring/Controlling, Closing).

Use Microsoft Project as the benchmark for drawing the points of comparison but without naming Microsoft Project as a possible selection in your list.

Back up each statement of comparison with a citation from a trustworthy public domain or scholarly source.

Organize the information such that it is searchable by process groups and by tools.

Give ECMS staff the permission to modify the information after publishing.

Non-Functional Requirements

Availability: published and available by 1 February 2026, usable in each semester.

Accessibility: available through lab computers as well as remotely using existing ECMS infrastructure without any need for additional infrastructure.

Quality: accurate, up-to-date, well-referenced content meeting ECMS's very high standard of quality.

Usability: prepared for students rather than PM experts.

Compliance: overall content of the PMS does not exceed 4,500 words.

Maintainability: designed in such a way that it is easy to make changes in future years.

## 7.0 Budget Estimate and Financial Analysis

This project is limited by the allotted budget of $200,000 which will be spent in Year 0 (2025) on developing and launching the Wiki. Other than this, the most important ongoing expenditure will be internet access charges for the approximately 500 students who will be working on the two PMS platforms in the ECMS Labs - $6/student/month in 2025 increasing at a rate of 10% each year till 2027. However, against this, the savings of $1,200,000/year in software-costs is anticipated by ECMS from the point that R&D teams switch to the SaaS PMS from license-based PMS starting from Year 1 (2026). It is assumed that this saving has been arrived at after taking into account the $15/user additional charge for using SaaS. Assuming a discount rate of 7%, the project gives a positive NPV of about $2.80M and an ROI of about 809% over the four-year period with a payback in the first 3 months of Year 1. Detailed calculations are provided in Exhibit A.

## 8.0 Schedule Estimate

Summary milestones as per brief:

Planning phase commences on 1 August 2025

Project implementation completed by 30 December 2025

Wiki launches 1 February 2026, before the start of Semester 1, 2026

The dates have been provided prior to the actual Semester 2, 2026, running of this course, and thus the dates shall be taken as they are, and later on confirmed with the lecturer to ascertain whether the whole timeline needs to move one year ahead. The schedule baseline, network diagram, and critical path analysis are discussed in Part 2 below.

## 9.0 Potential Risks

| Risk | Category | Response |
| --- | --- | --- |
| Chosen PMS pricing or features change before go-live | Technology | Re-verify vendor pricing close to publish date |
| Wiki content exceeds the 4,500-word cap | Scope | Draft comparison tables early; track word count weekly |
| Sources aren't credible enough to support claims | Quality | Cite only vendor docs, academic journals, or established PM publications |
| Enrolment or fee figures change before Semester 1, 2026 | Cost | Re-verify against ECMS before final submission |
| A team member is unavailable and a section slips | Resource | Team contract + weekly check-ins (see Team Contract) |

## 10.0 Exhibits

Exhibit A: Financial Analysis – See section 1.5 which comes after this document.

# 1.5. Exhibit A — Financial Analysis

Source: Templates/1.5. Exhibit A - Financial Analysis.csv (verified 20 Aug 2026)

| Metric | Year 0 (2025) | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | Total |
| --- | --- | --- | --- | --- | --- |
| Costs | 236,000.00 | 39,600.00 | 43,560.00 | 43,560.00 |  |
| Discount factor | 1.0000 | 0.9346 | 0.8734 | 0.8163 |  |
| Discounted costs | 236,000.00 | 37,009.35 | 38,046.99 | 35,557.94 | 346,614.27 |
| Benefits | 0.00 | 1,200,000.00 | 1,200,000.00 | 1,200,000.00 |  |
| Discount factor | 1.0000 | 0.9346 | 0.8734 | 0.8163 |  |
| Discounted benefits | 0.00 | 1,121,495.33 | 1,048,126.47 | 979,557.45 | 3,149,179.25 |
| Discounted benefits - costs (NPV) | (236,000.00) | 1,084,485.98 | 1,010,079.48 | 943,999.52 | 2,802,564.98 |
| Cumulative | (236,000.00) | 848,485.98 | 1,858,565.46 | 2,802,564.98 |  |

Discount rate: 7%   |   ROI: 808.6%   |   Payback: Year 1 (~2.6 months in)

# 2. Stakeholder Register

Source: Templates/2. stakeholder register-finished.docx (verified 20 Aug 2026)

Stakeholder Register

Authors: Mathew, Isaiah, Rahul, Bradley

Date:30/07/26

Project Name: PMS Comparison

| Name | Position | Internal/External | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| Mathew | Project Manager | Internal | Coordinates the project, assigns tasks, monitors progress | ftc7312@autuni.ac.nz |
| Isaiah | Project member | Internal | Conducts research and contributes to the report | kgb2156@autuni.ac.nz |
| Rahul | Project member | Internal | Assists with research, documentation and presentation | gpg6703@autuni.ac.nz |
| Bradley | Project member | Internal | Assists with analysis, editing and quality checking | fss2720@autuni.ac.nz |
| Manpreet Dhanjal | Project Supervisor | External | Provides groups/feedback and assesses the project | manpreet.kaur.dhanjal@aut.ac.nz |

# 3. Stakeholder Management Strategy

Reference: Templates/3. stakeholder management strategy.doc (validated on 20 Aug

| Name | Level of Interest | Level of Influence | Potential Management Strategies |
| --- | --- | --- | --- |
| ECMS Program Sponsor | High | High | Manage closely - fortnightly status updates, sign-off required at each milestone report (v1/v2); involve in setting the PMS selection criteria early so there are no surprises at review. |
| Project Team (Matthew, Isaiah, Rahul, Bradley) | High | High | Manage closely - weekly team meetings with agenda and minutes, RACI and roles fixed in the Team Contract and Project Charter, shared task tracker so interest and effort stay aligned. |
| R&D Course Coordinator | High | Medium-High | Manage closely - involve early in defining the evaluation criteria for the two PMS, since they'll assess R&D teams against the same standard; review the draft Wiki before it goes live. |
| R&D Students (Sem 1 and Sem 2 intake) | High | Low | Keep informed - no formal decision role, but the whole project exists for them; short intro/FAQ on the Wiki itself plus a launch announcement, and an informal feedback channel post-launch. |
| ECMS IT/Infrastructure Support | Medium | Medium | Keep satisfied - confirm early that current infrastructure covers Wiki hosting and lab access (per the business case assumption); loop in only at go-live or if a hosting issue comes up. |
| Selected SaaS PMS Vendors | Low | Low | Monitor - no direct engagement needed; check their public pricing/feature pages periodically before publish date in case anything changes. |

# 4. Project Charter incl. Roles & Responsibilities

Reference: Templates/4. Project Charter-final.docx (confirmed on 2

Project Charter

Writer(s): Isaiah, Matthew, Bradley, Rahul

Date: 07/30/26

Project Title: 	PMS Comparison

Project Start Date:  07/30/26                    Projected Finish Date: 08/23/26

Budget Details: NZD 200,000

Project Manager: Matthew Rushmer, Tel: 022 087 9529

Project Objectives: Create a wiki project where you can compare two different types of wikis that can suit the needs of R&D students.

Success Criteria:

The word limit for the wiki should be less than 4500 words.

Your project cannot go beyond the initial budget set aside.

Your project should be completed on time.

The wiki has to be clear and relevant to the R&D students.

Approach:

Planning - The team will fill 11 different documents among others including a project charter, a business case, a stockholder strategy paper and a financial analysis in order to have proper planning.

Designing - The team will create the wiki project following the process that has been planned out.

Review - We will conduct review meetings throughout the entire project to ensure that we stay within budget, scope and objectives of the project.

Feedback gathering - The team will gather a sample of current and past R&D students to provide feedback on the wiki. The feedback will be used to re-plan. Continue until it is satisfactory.

Delivery - The wiki website will be set up in the schools servers making it accessible. The R&D teachers will circulate the link of the website to the R&D students.

Procedure for change request:

Change request to the project manager by email.

In case of acceptance of the change by the project manager, the stakeholders mentioned above will immediately be informed.

The team will immediately revise the planning documents relevant to the change.

If required, the design of the wiki project will be revised according to the change made to the planning documents.

Issue management process:

In case the problem is not immediately fixable, send an email to the issue manager (Bradley currently).

This will be recorded on the issue management excel spreadsheet, which will contain all necessary information about the issue.

Issue management will also send an email to the concerned worker about the issue, as well as the project manager.

Once the issue is solved, the issue status will be changed to "resolved" and the solution will be entered in the comments section.

Roles and Responsibilities

| Name and Signature | Role | Position | Contact Information |
| --- | --- | --- | --- |
| Matthew Rushmer | Ensures team stays on track | Team Lead | ftc7312@autuni.ac.nz |
| Isaiah Thompson | Anylyzes the risks to better inform the team | Risk analyzer | kgb2156@autuni.ac.nz |
| Bradley Ah Sam | Keeps track of all the issues | Issue manager | fss2720@autuni.ac.nz |
| Rahul Shankar | Informs and advocates for the stakeholders | Stakeholder advisor | gpg6703@autuni.ac.nz |

Comments: (Comments written or typed by above-mentioned stakeholders, if any)

# 5. Team Contract

Source: Templates/5. Team Contract-final.docx (verified 20 Aug 2026)

Team Contract

Author: Mathew, Isaiah, Rahul,

Date: 30/07/26

Version: 1.2

Project Name: PMS Comparison

Name of Project Team Members and their Sign-offs:

| Name | Date |
| --- | --- |
| Mathew | 23/07/2026 |
| Isaiah | 23/07/2026 |
| Rahul | 23/07/2026 |
| Bradley | 23/07/2026 |

Code of Conduct: As a project team, we shall:

Complete our assigned work in time

Be a fair contributor to the project

Respect all members of the team

Participation: We will Attend all team meeting

Provide help where needed for the members of the team

Assume responsibility for our own assignments

Communication: We will:

Maintain a professional attitude

Always respond to the messages of the team within 24 hours

Keep team members informed about our progress on the assignments

Problem Solving: We will:

Discuss and settle any differences that may arise during the whole project

Listening to all contributions before making a decision.

Lecturer or TA should be asked for assistance where we can’t sort out the problem on our own

Meeting Guidelines: We will:

Meetings punctuality is highly encouraged

Stay focused during the whole meeting.

Document the following information of the meeting; date, purpose of the meeting, and people who attended the meeting

# 6. Kick-off Meeting Agenda & Minutes

Source: Templates/6. kick-off-meeting-final.docx (confirmed 20 Aug 2026)

Kick-Off Meeting

Authors: Isaiah, Matthew, Bradley, Rahul

Date: 07/30/2026

Project Name: PMS Comparison

Meeting Objective:

Let’s begin with the preparing stage of the project by going through the objective and important documents. Assign the documents to the team members.

Agenda:

Tallying of participants: Raphael was late due to car problems, while Bradley could not attend.

Exchanged contact information.

Reviewed objectives in terms of scope, time, and cost.

Documents relating to the project were assigned by Matthew. Next meeting, we will get more defined roles.

Concluded the meeting.

Used the rest of the time to work on the documents relating to the project.

List of action items for the meeting is provided below.

| Action Item | Assigned To | Due Date |
| --- | --- | --- |
| Business case | Matthew Rushmer | 05/08/26 |
| Stakeholder management strategy | Matthew Rushmer | 12/08/26 |
| Client meeting agenda/minutes | Matthew Rushmer | Ongoing |
| Project charter | Isaiah Thompson | 08/08/26 |
| Kick off meeting agenda/minutes | Isaiah Thompson | 07/30/26 |
| Risk register | Isaiah Thompson | Ongoing |
| Stakeholder Register | Rahul Shankar | 08/05/26 |
| Team contract | Rahul Shankar | 08/05/26 |
| Next team meeting agenda/minutes | Rahul Shankar | 08/05/26 |
| Issue register | Bradley | Ongoing |
| Milestone Report | Bradley | Ongoing |

Next Meeting Date and Time: 08/06/26

# 7. Client Meeting Agenda & Minutes

Source: Templates/7. Client Meeting_Template-final.docx (confirmed 22 Aug 2026)

## Client Meeting 1 — Thursday 23 July 2026

Client/Project: PMS Comparison

Objective: Follow-up from kick off meeting: finalize format for weekly meetings and PMS shortlist process

Meeting initiated by: Matthew Rushmer

Location: WS Building   |   Date: 23/07/2026   |   Time: 9:30am

QA: | Version: | Minutes Approved By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| None recorded |  |

Minutes prepared by: Matthew

Minutes distribution to: All project participants

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Confirm expectations for weekly check-ins with the TA | Matthew | 10 min |
| 2 | Review team roles from the Project Charter | Isaiah | 10 min |
| 3 | Agree criteria for shortlisting the two PMS candidates | Rahul | 15 min |
| 4 | Q&A / next steps | All | 10 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| None (first meeting) | None (first meeting) | None (first meeting) | None (first meeting) |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Matthew confirmed the weekly Thursday check-in slot with Manpreet as the ongoing TA/client contact. |
| 2 | No project documents had been produced yet, so the discussion stayed high-level: expectations for the weekly check-ins. |
| 3 | Agreed to formally assign roles and paperwork once the whole team could meet at the internal kickoff. |
| 4 | Rahul and Bradley agreed to start informal PMS candidate research ahead of that kickoff rather than waiting. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Book and hold the internal team kickoff | Matthew | 30/07/26 |
| 2 | Start informal PMS candidate research ahead of kickoff | Rahul & Bradley | 30/07/26 |
| 3 | Confirm full team availability for the weekly Thursday slot | All | 30/07/26 |

Next Meeting

Date: 30 July 2026 | Time: 9:30am

Points of discussion for next meeting:

• Review roles and paperwork assignments made at kickoff

• Confirm progress on PMS candidate research

• Discuss the business case draft status

Actions to discuss in the next meeting:

• Confirm role assignments from kickoff

• Report initial PMS research findings

• Agree next steps on the business case draft

TA Feedback (Week 1)

Good start. One comment: make sure that "PMS shortlisting" does not remain unprofessional for two consecutive weeks. Go in with at least some names on the table for candidates, even if they aren't perfect, so that you can come out of that meeting with a decision rather than another action point.

## Client Meeting 2 — Thursday 30 July 2026

Client/Project: PMS Comparison

Purpose: To do progress check on PMS shortlisting and business case draft

Called by: Matthew Rushmer

Location: WS Building   |   Date: 30/07/2026   |   Time: 9:30am

QA: | Version: | Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Bradley Ah Sam | Issue Manager |

Minutes prepared by: Rahul

Distribution of minutes to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Update on narrowing the two PMS candidates | Rahul | 10 min |
| 2 | Any blockers on research so far | All | 10 min |
| 3 | Business case draft status | Matthew | 15 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Book and hold the internal team kickoff | Matthew | Closed — held today |
| 2 | Start informal PMS candidate research ahead of kickoff | Rahul & Bradley | Closed — underway |
| 3 | Confirm full team availability for the weekly Thursday slot | All | Closed — confirmed |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | This week's meeting doubled as the internal team kickoff. |
| 2 | Reviewed the Assignment 1 Part 1 brief and marking criteria, and exchanged contact details. |
| 3 | Matthew was confirmed as project leader. |
| 4 | Documents were assigned: Matthew — Business Case, Stakeholder Management Strategy, Client Meeting Minutes; Isaiah — Project Charter, Kick-off Minutes, Risk Register; Rahul — Stakeholder Register, Team Contract, Team Meeting Minutes; Bradley — Issue Register, Milestone Report (assigned in his absence, to be briefed). |
| 5 | Bradley could not attend, and Rahul was separately delayed by car trouble. |
| 6 | The business case draft itself hadn't started yet — today's session was about ownership, not content. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Business Case | Matthew | 05/08/26 |
| 2 | Stakeholder Management Strategy | Matthew | 12/08/26 |
| 3 | Project Charter | Isaiah | 08/08/26 |
| 4 | Risk Register | Isaiah | Ongoing |
| 5 | Stakeholder Register & Team Contract | Rahul | 05/08/26 |
| 6 | Issue Register & Milestone Report (pending Bradley being briefed) | Bradley | Ongoing |

Next Meeting

Date: 6 August 2026 | Time: 9:43am

Agenda for next meeting:

• Update on stakeholder register / management strategy progress

• Confirm the two PMS finalists

• Check scope and word-count tracking against the 4,500-word cap

Action Items to discuss in next meeting:

• Confirm PMS finalists

• Provide progress update on the business case and stakeholder documents

• Flag any blockers before next week

TA Feedback (Week 2)

I need clear accountability of all the documents exactly like that. Couple of notes: First one is that Bradley did not attend the meeting and took responsibility of preparing two documents for which there was least amount of explanation provided so do make sure that he is properly briefed regarding these two or you will have to do this again in week 3. Secondly, "Ongoing" is not a due date, please provide one next time for Risk Register.

## Client Meeting 3 — Thursday 6 August 2026

Client/Project: PMS Comparison

Purpose: Document progress for stakeholders; Verify PMS finalists

Meeting initiated by: Rahul Shankar

Location: WS Building   |   Date: 06/08/2026   |   Time: 9:43am

Question and Answer: | Version: | Minutes Exam

Attendees

| Name | Representing |
| --- | --- |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |

Minutes prepared by: Rahul

Minutes distributed to: All project participants

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Stakeholder register / management strategy progress | Isaiah | 10 min |
| 2 | Confirm the two PMS finalists | Rahul / Bradley | 15 min |
| 3 | Check scope and word-count tracking against the 4,500-word cap | Matthew | 10 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Business Case | Matthew | In progress |
| 2 | Stakeholder Management Strategy | Matthew | In progress |
| 3 | Project Charter | Isaiah | In progress |
| 4 | Risk Register | Isaiah | Ongoing |
| 5 | Stakeholder Register & Team Contract | Rahul | In progress |
| 6 | Issue Register & Milestone Report | Bradley | Pending briefing |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Most of this session went into catching Bradley up rather than the planned PMS-finalist discussion. |
| 2 | Rahul walked Bradley through what was agreed at kickoff and explained the Issue Register and Milestone Report in detail. |
| 3 | Bradley was shown the expected due dates and how the documents should be completed, and asked clarifying questions. |
| 4 | Because the handover took priority, the two PMS finalists weren't formally confirmed this week. |
| 5 | Rahul and Bradley agreed to lock in the PMS finalists once Bradley's onboarding was complete. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | 13/08/26 |
| 2 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Update Matthew and Isaiah on Bradley's progress | Rahul | 13/08/26 |
| 5 | Confirm PMS finalists (carried over, now overdue) | Rahul & Bradley | 13/08/26 |

Next Meeting

Date: 13 August 2026 | Time: 9:21am

Discussion topics for the next meeting:

• Business case financials review (NPV / ROI / payback)

• Risk register v1 status

• Outstanding items before Part 1 submission

Next Meeting Agenda Items:

• Finalise PMS finalist confirmation

• Review business case financials

• Identify any remaining outstanding work

TA Feedback (Week 3)

You wasted your team meeting discussing what should have been a simple briefing on the project, since the other person had missed kickoff, instead of completing the finalist work for the PMS as I expected from you and which isn't an issue with Bradley, but an issue with handover. Just a brief note sent the day after kickoff could have prevented all of this. Lock down your finalists before next week as it is past due.

## Client Meeting 4 — Thursday 13 August 2026

Client/Project: PMS Comparison

Objective: Financial review of business case & risk register review

Meeting called by: Matthew Rushmer

Location: WS Buidling   |   Date: 13/08/2026   |   Time: 9:21am

QA: | Version: | Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |

Minutes prepared by: Rahul

Distribution of Minutes to: Project Team Members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Business case financials review (NPV / ROI / payback) | Matthew | 15 min |
| 2 | Risk register v1 status | Isaiah | 10 min |
| 3 | Outstanding items before Part 1 submission | All | 10 min |
| 4 | Next steps | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | Done — first draft presented |
| 2 | Prepare first draft of Milestone Report | Bradley | Done |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | In progress |
| 4 | Confirm PMS finalists | Rahul & Bradley | Confirmed |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | All members reported progress: Business Case, Stakeholder Register and Team Contract are underway. |
| 2 | Isaiah gave a Risk Register update. |
| 3 | Bradley presented first drafts of the Issue Register and Milestone Report, confirming he understood his responsibilities after last week's briefing. |
| 4 | The team flagged several documents still needing proofreading and formatting. |
| 5 | The final team meeting was scheduled for 20 August. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Die Geschäftsfälle und den Stakeholder Management Plan vervollständigen. | Matthew | 20/08/26 |
| 2 | Projektsforordning og Risikoregister op | Isaiah | 20/08/26 |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | 20/08/26 |
| 4 | Complete Issue Register and Milestone Report | Bradley | 20/08/26 |
| 5 | Proofread allocated documents prior to last meeting | All | 20/08/26 |

Next Meeting

Date: 20 August 2026 | Time: 9:15am

Issues for discussion in the next meeting:

• Part 1 completion status review (all 11 items)

• Outstanding items: Issue Register v1, Milestone Report v1

• Submission logistics and final checks

Action Points to be discussed in the next meeting:

• Confirm all 11 items are complete

• Resolve any remaining incomplete work

• Confirm submission responsibilities

TA Feedback (Week 4)

There is one week left to go and there are two documents that would need your attention – the business case and risk register – since financial mistakes are the easiest mistake that a marker can catch.

## Client Meeting 5 — Thursday 20 August 2026

Client/Project: PMS Comparison

Purpose: Final Part 1 readiness review

Called by: Matthew Rushmer

Location: WS Building   |   Date: 20/08/2026   |   Time: 9:15am

Q&A: | Version: | Minutes Reviewed By:

Attendees

| Name | Representing |
| --- | --- |
| Matthew Rushmer | Team Lead |
| Isaiah Thompson | Risk Analyzer |
| Rahul Shankar | Stakeholder Advisor |
| Bradley Ah Sam | Issue Manager |
| Manpreet Dhanjal | TA / Client Contact |

Absent

| Name | Representing |
| --- | --- |
| None recorded |  |

Minutes prepared by: Rahul

Distribution of minutes to: All members of the project team

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Part 1 completion status review (all 11 items) | Matthew | 10 min |
| 2 | Outstanding items: Issue Register v1, Milestone Report v1 | Bradley | 10 min |
| 3 | Submission logistics and final checks | All | 10 min |
| 4 | Next steps into Part 2 | All | 5 min |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy | Matthew | Due today |
| 2 | Update Project Charter and Risk Register | Isaiah | Due today |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | Due today |
| 4 | Finalise Issue Register and Milestone Report | Bradley | Due today |
| 5 | Proofread assigned documents | All | Due today |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | The team reviewed completion status across all 11 Part 1 items. |
| 2 | Updated the Risk Register and Issue Register where required. |
| 3 | Checked that document formatting and terminology were consistent across the pack. |
| 4 | A handful of minor spelling, formatting and wording issues were identified for correction. |
| 5 | Outstanding sections were assigned back to their owners for same-day fixes. |
| 6 | The team confirmed everything would be ready ahead of the 23 August deadline, with Matthew performing the final check before submission. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete final check of Business Case and full document set | Matthew | 22/08/26 |
| 2 | Complete final update of Risk Register | Isaiah | 22/08/26 |
| 3 | Complete and organise all team meeting documentation | Rahul | 22/08/26 |
| 4 | Complete final Issue Register and Milestone Report | Bradley | 22/08/26 |
| 5 | Review final project pack before submission | All | 22/08/26 |

Next Meeting

Date: Needs to be specified | Time: N/A - part 1 done

Topics to be discussed in the next meeting:

• Part 2 planning

• Carry forward learnings from Part 1

Items to be addressed in next meeting:

• Confirm Part 2 timeline once released

TA Feedback (Week 5)

Before submitting the work, please check the issue #1 in register. The deadline of issue #1 is prior to the deadline of the project itself. These types of errors can appear as mistakes in front of the marker, but content wise there is nothing wrong. Also make sure that these Client Meeting Minutes are attached, these are the documents I have seen students omitting in a hurry to attach everything else.

# 8. Team Meeting Agenda & Minutes

Source: Templates/8. Meeting_Minutes_Template_redo-final.docx (verified 21 Aug 2026)

.

## Team Meeting 1 — 06/08/26

Purpose: To work on assigned tasks and discuss any issues that may have come up regarding our assigned tasks.

Meeting initiated by: Mathew (Project Leader)

Location: AUT – WS220   |   Date: 06/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew | Version: 1.0 | Minutes reviewed by: Rahul

Attendees

| Name | Representing |
| --- | --- |
| Rahul |  |
| Bradley |  |

Absent

| Name | Representing |
| --- | --- |
| Isaiah | Project Member |
| Mathew | Project Leader |

Minutes prepared by: Rahul

Minutes circulated to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Update Bradley on the project | Rahul | 10 minutes |
| 2 | Explain Bradley’s assigned tasks | Rahul | 10 minutes |
| 3 | Discuss due dates and expectations | Rahul | 15 minutes |
| 4 | Explain how to complete the Issue Register and Milestone Report | Rahul | 10 minutes |
| 5 | Discuss next steps and questions | Rahul | 15 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete Business Case and related documents | Mathew | Ongoing |
| 2 | Complete Project Charter and Risk Register | Isaiah | Ongoing |
| 3 | Complete Stakeholder Register and Team Contract | Rahul | Ongoing |
| 4 | Complete Issue Register | Bradley | Ongoing |
| 5 | Complete Milestone Report | Bradley | TBA |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | Rahul updated Bradley on what had been discussed during the kick-off meeting. |
| 2 | Bradley was informed of the overall project requirements and submission deadline. |
| 3 | Rahul explained that Bradley had been assigned the Issue Register and Milestone Report. |
| 4 | The purpose and structure of the Issue Register were explained. |
| 5 | The purpose and structure of the Milestone Report were explained. |
| 6 | Bradley was shown the expected due dates and how the documents should be completed. |
| 7 | Bradley asked questions about his assigned tasks and clarified what was required. |
| 8 | Bradley agreed to begin working on his assigned documents before the next meeting. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Begin Issue Register | Bradley | 13/08/26 |
| 2 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |
| 3 | Continue Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Update Mathew and Isaiah on Bradley’s progress | Rahul | 13/08/26 |
| 5 | Review progress at next meeting | Rahul & Bradley | 13/08/26 |

Next Meeting

Date: 13/08/26 | Time: 8:00 AM – 10:00 AM

Discussion points for the next meeting:

Discuss the progress of Bradley in Issue Register and Milestone Report.

Discuss the progress of other project documents.

Any concerns or changes to be addressed before submitting the assignment.

Action items to be discussed during the next meeting:

Ensure that the assigned tasks are being performed on schedule.

Identify outstanding work.

Outline the remaining tasks before the deadline of 23rd August.

## Team Meeting 2 — 13/08/26

Purpose: Evaluation of assigned document progress and future planning for the final phase of the project.

Meeting initiated by: Mathew (Project Manager)

Location: AUT – WS220   |   Date: 13/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew | Version: 1.0 | Approved By: Mathew

Attendees

| Name | Representing |
| --- | --- |
| Mathew | Project leader |
| Isaiah | Project member |
| Bradley | Project member |
| Rahul | Project member |

Minutes prepared by: Rahul

Distribution of Minutes to: All project members

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Check progress on allocated project documents | All members | 20 minutes |
| 2 | Check progress on Bradley’s Issue Register and Milestone Report | Bradley | 15 minutes |
| 3 | Discusses risks, issues and incomplete work | All members | 10 minutes |
| 4 | Identify necessary changes prior to submission | Mathew | 15 minutes |
| 5 | Plan final week of project work | All members | 15 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finish Business Case and other relevant documentation | Mathew | 13/08/26 |
| 2 | Complete Project Charter and update Risk Register | Isaiah | 13/08/26 ongoing |
| 3 | Complete Stakeholder Register and Team Contract | Rahul | 13/08/26 |
| 4 | Prepare Issue Register | Bradley | 13/08/26 |
| 5 | Prepare first draft of Milestone Report | Bradley | 13/08/26 |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | All members provided an update on the progress of their assigned documents. |
| 2 | Bradley confirmed that he understood his responsibilities after being briefed at the previous meeting. |
| 3 | The team reviewed progress on the Business Case, Project Charter, Stakeholder Register and Team Contract. |
| 4 | Bradley presented progress on the Issue Register and Milestone Report. |
| 5 | Isaiah provided an update on risks identified in the Risk Register. |
| 6 | The team identified several documents that required final proofreading and formatting. |
| 7 | Members agreed to complete outstanding work before the final team meeting. |
| 8 | The final team meeting was scheduled for 20 August 2026. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finalise Business Case and Stakeholder Management Strategy | Mathew | 20/08/26 |
| 2 | Update Project Charter and Risk Register | Isaiah | 20/08/26 |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation | Rahul | 20/08/26 |
| 4 | Finalise Issue Register and Milestone Report | Bradley | 20/08/26 |
| 5 | Proofread assigned documents before final meeting | All members | 20/08/26 |

Next Meeting

Date: 20/08/26 | Time: 8:00 AM – 10:00 AM

Points to be discussed at the next meeting:

Discussion of all Part 1 documents prepared.

Format and double-check for accuracy and consistency.

Verify that all aspects are finalized.

Action Items to be discussed at the next meeting:

Ensure that all outstanding incomplete tasks are completed.

Complete final proofreading.

Confirm submission responsibilities.

## Team Meeting 3 — 20/08/26

Objective: Final preparation of Assignment 1 Part 1 documents.

Call made by: Mathew (Project Leader)

Location: AUT – WS220   |   Date: 20/08/26   |   Time: 8:00 AM – 10:00 AM

QA: Mathew | Version: 1.0 | Minutes Approved by: Mathew

Attendees

| Name | Representing |
| --- | --- |
| Mathew | Project leader |
| Isaiah | Project member |
| Bradley | Project member |
| Rahul | Project member |

Minutes prepared by: Rahul

Distribution of minutes to: All members of the project

Agenda

| # | Agenda Item Description | Owner | Time Allotted |
| --- | --- | --- | --- |
| 1 | Review completion status of all Part 1 documents | Mathew | 20 minutes |
| 2 | Review risk and issue registers | Isaiah & Bradley | 15 minutes |
| 3 | Proofread and check document consistency | All members | 10 minutes |
| 4 | Identify and correct final issues | All members | 15 minutes |
| 5 | Confirm submission plan and responsibilities | Mathew | 10 minutes |

Open Action Items / Action Items from the Previous Meeting

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Finish Business Case and Stakeholder Management Strategy |  |  |
| 2 | Update Project Charter and Risk Register |  |  |
| 3 | Finalise Stakeholder Register, Team Contract and meeting documentation |  |  |
| 4 | Finalise Issue Register and Milestone Report |  |  |
| 5 | Proofread assigned project documents |  |  |

Discussion and Decisions

| # | Discussion and Decisions |
| --- | --- |
| 1 | The team reviewed the status of all documents required for Assignment 1 Part 1. |
| 2 | Each member confirmed the completion status of their assigned work. |
| 3 | The Risk Register and Issue Register were reviewed and updated where required. |
| 4 | The team checked that document formatting and terminology were consistent. |
| 5 | Minor spelling, formatting and wording issues were identified for correction. |
| 6 | Outstanding sections were assigned to the responsible team member for final completion. |
| 7 | The team confirmed that all documents would be completed before the 23 August deadline. |
| 8 | Mathew would perform the final check before submission. |

Summary of Action Items

| # | Action Item Description | Owner | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Complete final check of Business Case and project documents | Mathew | 22/08/26 |
| 2 | Complete final update of Risk Register | Isaiah | 22/08/26 |
| 3 | Complete and organise all team meeting documentation | Rahul | 22/08/26 |
| 4 | Complete final Issue Register and Milestone Report | Bradley | 22/08/26 |
| 5 | Review final Project Wiki before submission | All members | 22/08/26 |

Next Meeting

Date: 23/08/26 | Time: 11:30 PM

Points to be discussed in the next meeting:

Final submission check.

Ensure that all documents are included.

Confirmation of successful submission of Assignment 1 Part 1.

Items of action to be discussed in the next meeting:

Confirmation of all required documents.

Confirmation of the final draft.

Submission of Assignment 1 Part 1.

# 9. Risk Register (v1)

References: Templates/9. risk register version 1-final.xlsx (verified on 20 August

| ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | Stakeholder confusion | Stakeholders confused and not informed about the project | Third-Party risk | Not planning with stakeholders in mind | Lack of stakeholder meetings | Set up a meeting with stakeholders to discuss progress. | Rahul Shankar | 4 | 3 | closed |
| 2 | 5 | Above word count | Wiki page above the 4500 word limit. | Scope risk | Not writing with scope in mind | Lack of conciseness, over bloated wording. | Proof read to make sure everything is essential and brief | Matthew Rushmer | 2 | 4 | open |
| 3 | 1 | Above budget | Going above the 200,000$ budget for the wiki page | Financial Risk | Lavish spending | Lack of proper financial spending and plan | Keep Financial documents updated with budget in mind and go over spending during meetings | Matthew Rushmer | 1 | 5 | closed |
| 4 | 3 | Project due date | Delivering the wiki page past the given date. | Schedule Risk | Not enough work hours | Lack of workers. Poor management of current workers | Higher more people. Start assigning more hours to current workers. | Matthew Rushmer | 3 | 5 | open |
| 5 | 4 | Offline servers | Server outages preventing the users from accessing the site | Operational Risk | unreliable server. | Lack of backup servers. | Setup multiple hosts for the wiki page. | Bradley Ah Sam | 3 | 4 | open |

# 10. Issue Register (v1)

Template Source: 10 Issue Log Version 1.xls (Validated 21 Aug

| Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Hard to find good PMS information | May delay research | Week 2 | Bradley Ah Sam | Team Leader | M | 10/08/26 | Open | N/A |
| 2 | Team members have different schedules | May delay meeting | Week 5 | Bradley Ah Sam | Team Leader | L | 20/08/26 | Open | N/A |
| 3 | Team roles are unclear | Work may be missed | Week 1-2 | Bradley Ah Sam | Entire Team | M | 28/07/26 | Open | N/A |
| 4 | Some tasks may be late | Might delay Part 1 | Week 5-6 | Bradley Ah Sam | Entire Team | H | 23/08/26 | Open | N/A |

# 11. Milestone Report (v1)

Source: Templates/11. milestone report.doc (checked on 21

Author: Bradley Ah Sam

Date: 07/08/26

| Milestone | Timeframe | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| Project team formed | Week 1 | Completed | Entire team |  |
| Roles and responsibilities assigned | Week 1-2 | Completed | Entire team |  |
| Kick off meeting | Week 1-2 | Completed | Mathew Rushmer |  |
| Business case | Week 3 | Completed | Mathew Rushmer |  |
| Stakeholder register | Week 3-4 | Completed | Rahul Shankar |  |
| Stakeholder management strategy completed | Week 3 | Completed | Mathew Rushmer |  |
| Project charter | Week 5 | Completed | Entire Team |  |
| Team contract signed | Week 4-5 | Completed | Entire Team |  |
| Risk register (Version 1) | Week 4 | Completed | Isaiah Thompson |  |
| Issue register (Version 1) | Week 6 | Completed | Bradley Ah Sam |  |
| Team meetings | Week 6 | Ongoing | Entire Team | Scheduling a time for all team members |
| Milestone report (Version 1) | Week 6 | Completed | Bradley Ah Sam |  |
| Part 1 ready for submission | Week 6 | Upcoming | Entire Team |  |