## Sheet1
Risk Register for Project Name
Date
Project Name:
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 2 | Stakeholder confusion | Stakeholders confused and not informed about the project | Third-Party risk | Not planning with stakeholders in mind | Lack of stakeholder meetings | Set up a meeting with stakeholders to discuss progress. | Rahul Shankar | 4 | 3 | closed
2 | 5 | Above word count | Wiki page above the 4500 word limit. | Scope risk | Not writing with scope in mind | Lack of conciseness, over bloated wording. | Proof read to make sure everything is essential and brief | Matthew Rushmer | 2 | 4 | open
3 | 1 | Above budget | Going above the 200,000$ budget for the wiki page | Financial Risk | Lavish spending | Lack of proper financial spending and plan | Keep Financial documents updated with budget in mind and go over spending during meetings | Matthew Rushmer | 1 | 5 | closed
4 | 3 | Project due date | Delivering the wiki page past the given date. | Schedule Risk | Not enough work hours | Lack of workers. Poor management of current workers | Higher more people. Start assigning more hours to current workers. | Matthew Rushmer | 3 | 5 | open
5 | 4 | Offline servers | Server outages preventing the users from accessing the site | Operational Risk | unreliable server. | Lack of backup servers. | Setup multiple hosts for the wiki page. | Bradley Ah Sam | 3 | 4 | open