Scope Statement

Author: Rahul Shankar

Date: 14/09/2026

Version: 1.0

Project Title: PMS Comparison Date: 14/09/2026 Prepared by: Rahul Shankar

Project Justification: The purpose of the PMS Comparison project is to help R&D students choose a suitable Project Management System. At the moment, students do not have consistent guidance on which PMS would be suitable for their projects, so they may have to spend extra time researching different options themselves. This can also lead to students choosing different tools without knowing which ones are most suitable. The project will address this by creating a Wiki that compares two cloud-based PMS platforms and gives students useful information to help them make a decision.

Product Characteristics and Requirements: The final product will be a Wiki aimed at R&D students. It will compare two cloud-based Project Management Systems and explain how they can be used across the five project management process groups: Initiating, Planning, Executing, Monitoring/Controlling and Closing. The information should be easy for students to understand and supported by reliable sources. - 1. Functional Requirement 1: The Wiki must explain the criteria used to choose the two PMS platforms. - 2. Functional Requirement 2: The Wiki must compare the two PMS platforms across all five project management process groups. - 3. Functional Requirement 3: Information used in the comparison must be supported by reliable sources such as vendor information or scholarly sources. - 4. Functional Requirement 4: The Wiki must organise the information so students can find content by PMS platform and project management process group. - 5. Non-Functional Requirement: The Wiki must be easy to understand and suitable for R&D students who may not have advanced project management knowledge.

Product User Acceptance Criteria:

Time:

The PMS Comparison Wiki must be completed and ready for use by February 1st 2027.

Scope:

The Wiki must compare exactly two cloud-based PMS platforms, cover all five project management process groups and stay within the 4,500-word limit. Microsoft Project will not be selected as one of the two PMS platforms.

Stakeholder:

The final Wiki should be reviewed by the relevant ECMS/R&D stakeholder before it is released. Any important feedback or changes identified during the review should be completed before the Wiki is considered finished.

Summary of Project Deliverables Project management-related deliverables:

The project management deliverables will include the Business Case, Project Charter, Team

Contract, Scope Statement, Work Breakdown Structure (WBS), project schedule, cost baseline, Risk Register, Issue Register, status or milestone reports, meeting minutes, final project presentation, final project report and lessons-learned report.

Product-related deliverables:

1. PMS Comparison Wiki

A completed Wiki that compares the two selected cloud-based Project Management Systems.

- PMS Comparison Research

Research and comparison of the two PMS platforms across the five project management process groups, supported by reliable sources.

- PMS Selection and Recommendations

The criteria used to select the two PMS platforms, along with findings explaining why they are suitable options for R&D students.