## Sheet1
Risk Register for Project Name
Date
Project Name:
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 2 | Stakeholder confusion | Stakeholders confused and not informed about the project | Third-Party risk | Not planning with stakeholders in mind | Lack of stakeholder meetings | Set up a meeting with stakeholders to discuss progress. | Rahul Shankar | 4 | 3 | closed
2 | 5 | Above word count | Wiki page above the 4500 word limit. | Scope risk | Not writing with scope in mind | Lack of conciseness, over bloated wording. | Proof read to make sure everything is essential and brief | Matthew Rushmer | 2 | 4 | open
3 | 1 | Above budget | Going above the 200,000$ budget for the wiki page | Financial Risk | Lavish spending | Lack of proper financial spending and plan | Keep Financial documents updated with budget in mind and go over spending during meetings | Matthew Rushmer | 1 | 5 | closed
4 | 3 | Project due date | Delivering the wiki page past the given date. | Schedule Risk | Not enough work hours | Lack of workers. Poor management of current workers | Higher more people. Start assigning more hours to current workers. | Matthew Rushmer | 3 | 5 | open
5 | 4 | Offline servers | Server outages preventing the users from accessing the site | Technology Risk | unreliable server. | Lack of backup servers. | Setup multiple hosts for the wiki page. | Bradley Ah Sam | 3 | 4 | open
6 | 2 | User data leakage | Login and other miscillanous user information being stolen | Technology risk | Insecure network | Hackers infaltrating the network. | Higher cyber-security proffesionals. | Matthew Rushmer | 2 | 5 | open
7 | 3 | Wiki page edited incorrectly. | Users of the wiki page editing the article to include innacurate or innapropriate information. | Technology risk | User gets writing permission to article. | Website bug or User gets team member account information. | Ensure that no user has write permission. Remind team members to not share account details. | Matthew Rushmer | 3 | 3 | open
op | 5 | Stakeholder intrests not represented | Stakeholders should feel like their needs are met. | Third-Party risk | Impropper stakeholder communication. | unproductive stake holder meetings. | Ensure the stakeholder meetings are long enough. When possible get team lead into the stakeholder meetings as well. | Rahul Shankar | 2 | 2 | closed
9 | 4 | Spelling errors in wiki project | It is likely that the wiki project will have a couple spelling errors which will hurt readability and our reputation | Reputational risk | Not writing carefully. | Lack of proof reafing. | Higher proof readers or get existing members to check eachothers work | Isaiah Thompson | 4 | 2 | open
10 | 5 | Wiki project not engaging. | An unengaging boring wiki project will leave its users forgetting the information shortly after read. | Strategic risk | Unintresting visual design | No thought put into drawing the reader in. | Consult a front end website developer. | Matthew Rushmer | 2 | 1 | open