## Slide 1: COMP507 IT Project Management Resource Management

## Slide 2: Agenda
The Importance of Project Resource Management
Six major resource management processes:
  Planning resource management
  Estimating activity resources
    Resource levelling
    Load balancing and greedy algorithm
  Acquiring resources
  Developing the project team
  Managing the project team
  Controlling resources
Notes: Art and science

## Slide 3: The Importance of Resource Management
People determine the success and failure of organizations and projects
  Most project managers agree that managing human resources effectively is one of the toughest challenges they face
  Managing people is a vital component of project resource management

## Slide 4: The Global IT Workforce
Although there have been ups and downs in the IT labor market, there will always be a need for good IT workers
  By June of 2017, there were almost 4.3 billion mobile-broadband subscriptions
  By 2020, ICT spending is projected to grow to nearly $5.5 trillion
  Jobs available to IT professionals are expected to increase by 12 percent by 2024
  Project management is number three on Computerworld’s hottest tech list

## Slide 5: What is Project Resource Management? (1 of 2)
Making the most effective use of the human and physical resources involved with a project
  Planning resource management
  Estimating activity resources
  Acquiring resources
  Developing the project team
  Managing the project team
  Controlling resources

## Slide 6: Keys to Managing and Leading People
Psychologists and management theorists have devoted much research and thought to the field leading people at work
  Motivation theories
  Influence and power
  Effectiveness
  Emotional intelligence
  Leadership

## Slide 7: Motivation Theories
Intrinsic motivation causes people to participate in an activity for their own enjoyment
  Example: some people love to read, write, or play an instrument because it makes them feel good
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
  Example: some young children would prefer not to play an instrument, but they do because they receive a reward or avoid a punishment for doing so

## Slide 8: Maslow’s Hierarchy of Needs (1 of 2)
Abraham Maslow argued that humans possess unique qualities that enable them to make independent choices, thus giving them control of their destiny
  Developed a hierarchy of needs; states that people’s behaviors are guided or motivated by a sequence of needs

## Slide 9: Maslow’s Hierarchy of Needs (2 of 2)

## Slide 10: Herzberg’s Motivational-Hygiene Theory (1 of 2)
Frederick Herzberg distinguished between motivational factors and hygiene factors
  Motivational factors: factors that cause job satisfaction
  Hygiene factors: could cause job dissatisfaction

## Slide 11: Herzberg’s Motivational-Hygiene Theory (2 of 2)
Hygiene Factors | Motivators
Larger salaries | Achievement
More supervision | Recognition
More attractive work environment | Work itself
Computer or other required equipment | Responsibility
Health benefits | Advancement
Training | Growth

## Slide 12: McClelland’s Acquired-Needs Theory
Specific needs are acquired or learned over time and shaped by life experiences
  Achievement (nAch): achievers like challenging projects with achievable goals and regular feedback
  Affiliation (nAff): people with high nAff desire harmonious relationships and need to feel accepted by others, so managers should try to create a cooperative work environment for them
  Power: (nPow): people with a need for power desire either personal power (not good) or institutional power (good for the organization)

## Slide 13: McGregor’s Theory X and Y
Douglas McGregor popularized the human relations approach to management in the 1960s
  Theory X: assumes workers dislike and avoid work, so managers must use coercion, threats and various control schemes to get workers to meet objectives
  Theory Y: assumes individuals consider work as natural as play or rest and enjoy the satisfaction of esteem and self-actualization needs
  Theory Z: introduced in 1981 by William Ouchi and is based on the Japanese approach to motivating workers, emphasizing trust, quality, collective decision making, and cultural values

## Slide 14: Influence and Power (1 of 3)
Thamhain and Wilemon: ways to have influence on projects
  Authority: legitimate hierarchical right to issue orders
  Assignment: ability to influence a worker's later work assignments
  Budget: ability to authorize others' use of discretionary funds
  Promotion: ability to improve a worker's position
  Money: ability to increase a worker's pay and benefits
  Penalty: ability to cause punishment
  Work challenge: ability to assign work that capitalizes on a worker's enjoyment of doing a particular task
  Expertise: perceived special knowledge that others deem important
  Friendship: ability to establish friendly personal relationships between the project manager and others

## Slide 15: Influence and Power (2 of 3)
Ways to influence
  Project managers who use work challenges and expertise to influence people projects are more likely to succeed
  Projects are more likely to fail when project managers rely too heavily on authority, money, or penalty

## Slide 16: Influence and Power (3 of 3)
Power is the potential ability to influence behavior to get people to do things they would not otherwise do
Types of power
  Coercive
  Legitimate
  Expert
  Reward
  Referent (role model)

## Slide 17: Covey and Improving Effectiveness (1 of 2)
Project managers can apply Covey’s seven habits to improve effectiveness on projects
  Be proactive
  Begin with the end in mind (have a clear vision)
  Put first things first
  Think win/win
  Seek first to understand, then to be understood
  Synergize
  Sharpen the saw

## Slide 18: Covey and Improving Effectiveness (2 of 2)
Good project managers are empathic listeners
  They listen with the intent to understand
Before you can communicate with others, you have to have rapport
  Relation of harmony, conformity, accord, or affinity
Mirroring is the matching of certain behaviors of the other person
  A technique to help establish rapport
IT professionals need to develop empathic listening and other people skills to improve relationships with users and other stakeholders

## Slide 19: Emotional Intelligence
Howard Gardner’s book Frames of Mind: The Theory of Multiple Intelligences introduced the concept of using more than one way to think of and measure human intelligence
  Emotional intelligence (EI) is knowing and managing one’s own emotions and understanding the emotions of others for improved performance

## Slide 20: Developing the Resource Management Plan and Team Charter
Involves identifying and documenting project resources, roles, responsibilities, skills, and reporting relationships
  Can be separated into a human resource management plan and a physical resource management plan
Contents include:
  Project organizational charts
  Responsibility assignment matrixes
  Staffing management plan and resource histograms
  Team charters

## Slide 21: organizational charts

## Slide 22: Assignment workflow

## Slide 23: Responsibility assignment matrixes

## Slide 24: RACI (Responsibility, Accountability, Consultation, Informed) chart
 | Car Owner | Shop Owner | Mechanic | Parts Supplier
Pay for parts and services | A, R | C |  | 
Determine parts and services needed | C |  | A, R | C
Supply parts |  | C | C | A, R
Install parts | I | A | R | 
Table 9-2 Sample RACI chart

## Slide 25: Resource histogram

## Slide 26: Estimating Activity Resources
Tools that can assist in resource estimating
  Expert judgment
  Various estimating approaches
  Data analysis
  Project management software
  Meetings

## Slide 27: Resource Loading (1 of 2)
Resource loading refers to the amount of individual resources an existing schedule requires during specific time periods
  Helps project managers develop a general understanding of the demands a project will make on the organization’s resources and individual people’s schedules
A resource is said to be overallocated when he/she is assigned more work than the actual capacity within a given time.

## Slide 28: Resource Loading (2 of 2)

## Slide 29: Resource Leveling (1 of 2)
Resource leveling is a technique for resolving resource conflicts by delaying tasks
  Main purpose is to create a smoother distribution of resource usage
Benefits of resource leveling
  When resources are used on a more constant basis, they require less management
  May enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
  Results in fewer problems for project personnel and accounting department
  Often improves morale

## Slide 30: Resource Leveling (2 of 2)

## Slide 31: Load Balancing
J. Kleinberg and E. Tardos, Algorithm Design, Person-Addison Wesley.

## Slide 32: Example
https://www.otfried.org/courses/cs500/slides-approx.pdf
Can you find the optimal makespan L*?

## Slide 33: Greedy Algorithm

## Slide 34: Greedy algorithm analysis

## Slide 35: Greedy algorithm analysis

## Slide 36: Greedy algorithm analysis

## Slide 37: Developing the Project Team (1 of 2)
The main goal of team development is to help people work together more effectively to improve project performance
  It takes teamwork to successfully complete most projects
Tuckman model describes five stages of team development
  Forming
  Storming
  Norming
  Performing
  Adjourning

## Slide 38: Developing the Project Team (2 of 2)
Training
  Project managers often recommend that people take specific training courses to improve individual and team development
Team-building activities
  Physical challenges
  Psychological preference indicator tools

## Slide 39: The Meyers-Briggs Type Indicator
Popular tool for determining personality preferences and helping teammates understand each other
Four dimensions
  Extrovert/Introvert (E/I)
  Sensation/Intuition (S/N)
  Thinking/Feeling (T/F)
  Judgment/Perception (J/P)
Intuitive/Thinking types (i.e., NTs or rationals) are attracted to technology fields

## Slide 40: The Social Styles Profile
People are perceived as behaving primarily in one of four zones, based on their assertiveness and responsiveness
  Drivers
  Expressives
  Analyticals
  Amiables

## Slide 41: Reward and Recognition Systems
Team-based reward and recognition systems can promote teamwork
  Focus on rewarding teams for achieving specific goals
    If management rewards teamwork, they will promote or reinforce the philosophy that people work more effectively in teams
Project managers must continually assess their team’s performance
  When they find areas in which individuals or the entire team can improve, it’s their job to find the best way to develop their people and improve performance

## Slide 42: Tools and Techniques for Managing Project Teams (1 of 4)
Several tools and techniques are available to assist in managing project teams
  Interpersonal and team skills
  Project management information systems
  Conflict management

## Slide 43: Tools and Techniques for Managing Project Teams (2 of 4)
Conflict handling modes
  Confrontation: directly face a conflict using a problem-solving approach
  Compromise: use a give-and-take approach
  Smoothing: de-emphasize areas of difference and emphasize areas of agreement
  Forcing: win-lose approach
  Withdrawal: retreat or withdraw from an actual or potential disagreement
  Collaborating: decision makers incorporate different viewpoints and insights to develop consensus and commitment

## Slide 44: Tools and Techniques for Managing Project Teams (3 of 4)

## Slide 45: Tools and Techniques for Managing Project Teams (4 of 4)
Conflict can be good
  Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
  Groupthink: conformance to the values or ethical standards of a group; can develop if there are no conflicting viewpoints
  Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 46: General Advice on Managing Teams
General advice
  Be patient and kind with your team
  Fix the problem instead of blaming people
  Establish regular, effective meetings
  Allow time for teams to go through the basic team-building stages
  Limit the size of work teams to three to seven members
  Plan some social activities to help project team members and other stakeholders get to know each other better
  Stress team identity
  Nurture team members and encourage them to help each other
  Acknowledge individual and group accomplishments
  Take additional actions to work with virtual team members

## Slide 47: Controlling Resources
Ensuring physical resources assigned to the project are available as planned
  Also involves monitoring the planned versus actual resources utilization and taking corrective actions as needed