## Slide 1: COMP507 IT Project Management Project Scope Management

## Slide 2
Team Contract
Have posted a sample on Canvas with the assignment 1 specification.
Use it to write the team contract for your assignment 1
To list your team’s specific code of ethics items, refer to PMI’s code of ethics
https://www.pmi.org/-/media/pmi/documents/public/pdf/ethics/pmi-code-of-ethics.pdf?rev=6af21906e5934b638ceeabeb4137f41d&sc_lang_temp=en
Team contract defines how the team will collectively work for the common goal and how the team will treat each on the project. Team contract helps to define the team culture (values, beliefs, attitudes, and behaviour)

## Slide 3: What is Project Scope Management?
Understand scope management
Describe the scope statement document
Discuss a Work Breakdown Structure (WBS)
Explain the importance of validating scope i.e. monitoring and controlling scope

## Slide 4: What is Scope?
Project Scope refers to all the work and processes involved in creating the product. Usually, it refers to:
  Functional requirements
  Non-functional requirements
  Regulatory requirements
  PM methodology (phases, method and practices)
  The product & related deliverables, i.e., product artefacts
  Project-related deliverables - project artefacts such as project plans, architecture plans, research reports/documents, test data, etc.
  Success factors
A deliverable is an artefact produced as part of a project, such as hardware or software, planning documents (Stakeholder register, stakeholder strategy management document, risk register, scope statement document, etc.), or meeting minutes.

## Slide 5: What is Project Scope Management?
Project scope management:
  processes (project management tasks) involved in planning, executing, and monitoring & controlling what is to be part of the project.
  Planning the scope: defining boundaries and establishing a foundational roadmap. This involves gathering stakeholder requirements to create a project scope statement and a Work Breakdown Structure (WBS), which together form the scope baseline
  Executing the scope: performing the actual work as defined in the project plan. During this phase, the project team uses the scope statement and WBS as a continuous reference to ensure all efforts remain focused on the approved deliverables
  Monitor and control of scope: preventing scope creep and managing changes. This phase runs in parallel with execution and involves benchmarking actual performance against the scope baseline to identify deviations.

## Slide 6: Scope Management Processes (PM Tasks)
Planning:
1. Create a scope statement document (a high-level plan which has high-level requirements)
- reviewing the project specification, including the business case and project charter, to capture the functional &
non-functional requirements, the product & project related deliverables, etc. to create a scope statement document
  Scope statement document
    Defines the total amount of work that will be done in the project
    Agreement on the project work (deliverables) between the project team and the sponsor.
    Not rigid – can change
2. Creating a WBS: a model that will identify project phases and tasks (project life cycle). Hence, using the WBS, the project schedule, quality assurance (QA) plan and budget must also be planned
Planning PM task is carried out in the planning phase of a project
Executing; scope statement document, schedule, QA and budget plans are executed
1. Collecting requirements: Analyzing and documenting the requirements that will be implemented. The deliverable will be the requirements document or product backlog (agile approach- product backlog). Done in the analysis and design phases
  2 Planning for implementation (agile: sprint/iteration plans). Done in the design phase just before starting the development and testing phase.
  Execution PM task will be carried out in the analysis, design, and implementation (development & testing) phases

## Slide 7: Scope Management Processes
Analysis and design phases must be monitored & controlled (M/C) to create requirements document or product backlog
Development and testing phases- must M/C the development & testing work done based on the requirements document or product backlog, including your schedule, scope statement document, quality assurance plan, etc.
M/C to validate the scope:
- Control (QC) implementation (based on sprint or iteration plan including product backlog) b based on the Quality Assurance (QA) plan
- Controlling changes to project scope throughout the life of the project [well
established change management request processes]
- formalizing acceptance of the project deliverables
- [stakeholder certifying and signing off after implementation]

## Slide 8: Scope Management Processes

## Slide 9: Scope Statement document- a high-level plan (planning process group)
One of the key PM tasks (process) to ensure a scope statement doc is developed
It captures all work required to be done in a project
Hence, an agreement between the team and product manager on what will be delivered
Prevents scope creep
Good scope definition is linked to project success
  improves the accuracy of time, cost, and resource estimates
  defines a baseline for performance management and project control
  aids in clearly communicating work responsibilities
Key input for preparing project scope statement
  Business case
  Scope specification or description provided
  Project charter
  Lesson learned reports
  Policies and procedures related to the scope statement document

## Slide 10: Scope Statement Document
Template- Scope Statement Document
Key elements of the project scope statement document:
  Product scope description/justification (a paragraph - 2 or 3 sentences)
  Product characteristics and requirements
    Functional requirements
    Non-functional requirements
  Product user acceptance criteria or project success factors
  All product deliverables
  All project deliverables
For your assignment, refer to the template for the scope statement document

## Slide 11
Project Title: Date: Prepared by:
Project Justification:
Product Characteristics and Requirements:
Product User Acceptance Criteria: Summary of Project Deliverables Project management-related deliverables: business case, charter, team contract, scope statement, WBS, schedule, cost baseline, status reports, final project presentation, final project report, lessons-learned report, and any other documents required to manage the project. Product-related deliverables: research reports, design documents, software code, hardware, etc. 1. 2. 3.

## Slide 12: Assignment 1- Project Scope
The Wiki project requires providing a review of two (2) cloud-based PMS (must not include Microsoft Project). Your project team must provide the criteria in the Wiki that your team has used to identify the two most suitable PMS for the R&D students. For the two selected PMS, the wiki must describe and compare at least one key feature/functionality across each of the process groups of Initiating, Planning, Executing, Monitoring/Controlling, and Closing projects. You may have to investigate Microsoft Project 2019 for its features and functionalities to be able to identify elements that you will use to provide information on and compare the two cloud-based PMS. The Wiki must be supported by related materials sourced from trusted public domain resources and academic journals. SECMS expects a very high-quality Wiki. Hence, your team must identify and clearly state the quality goals in the scope statement document. The word length of this Wiki project (information on two PMS) is expected to be no more than 4,500 words.

## Slide 13: Assignment 1- Project Scope
The Wiki project requires providing a review of two (2) cloud-based PMS (must not include Microsoft Project). Your project team must provide the criteria in the Wiki that your team has used to identify the two most suitable PMS for the R&D students. For the two selected PMS, the wiki must describe and compare at least one key feature/functionality across each of the process groups of Initiating, Planning, Executing, Monitoring/Controlling, and Closing projects. You may have to investigate Microsoft Project 2019 for its features and functionalities to be able to identify elements that you will use to provide information on and compare the two cloud-based PMS. The Wiki must be supported by related materials sourced from trusted public domain resources and academic journals. SECMS expects a very high-quality Wiki. Hence, your team must identify and clearly state the quality goals in the scope statement document. The word length of this Wiki project (information on two PMS) is expected to be no more than 4,500 words.

## Slide 14: Assignment 1- Project Scope
The Wiki project requires providing a review of two (2) cloud-based PMS (must not include Microsoft Project).
Functional requirements
1. Your project team must provide the criteria in the Wiki that your team has used to identify the two most suitable PMS for the R&D students.
2. For the two selected PMS, the wiki must describe and compare at least one key feature/functionality across each of the process groups of Initiating, Planning, Executing, Monitoring/Controlling, and Closing projects. You may have to investigate Microsoft Project 2019 for its features and functionalities to be able to identify elements that you will use to provide information on and compare the two cloud-based PMS
3. The Wiki must be supported by related materials sourced from trusted public domain resources and academic journals.
4. The word length of this Wiki project (information on two PMS) is expected to be no more than 4,500 words.
Non-functional requirements
1. SECMS expects a very high-quality Wiki. Hence, your team must identify and clearly state the quality goals in the scope statement document.

## Slide 15: Assignment 1- Project Scope (high-level requirements)
The Wiki project requires providing a review of two (2) cloud-based PMS (must not include Microsoft Project).
Functional requirements
1. Your project team must provide the criteria in the Wiki that your team has used to identify the two most suitable PMS for the R&D students.
2. For the two selected PMS, the wiki must describe and compare at least one key feature/functionality across each of the process groups of Initiating, Planning, Executing, Monitoring/Controlling, and Closing projects. You may have to investigate Microsoft Project 2019 for its features and functionalities to be able to identify elements that you will use to provide information on and compare the two cloud-based PMS
3. The Wiki must be supported by related materials sourced from trusted public domain resources and academic journals.
4. The word length of this Wiki project (information on two PMS) is expected to be no more than 4,500 words.
Non-functional requirements
1. SECMS expects a very high-quality Wiki. Hence, your team must identify and clearly state the quality goals in the scope statement document.

## Slide 16: Assignment 1- high-level requirements
Must properly be captured as high-level requirements based on certain rules
- Shall, Will, and Should is the standard requirements terminology
Functional requirements
1. The Wiki shall provide the criteria used to identify the two most suitable PMS for the R&D students.
2. For the two PMS, the wiki should describe and compare at least one key feature/functionality across each of the process groups of Initiating, Planning, Executing, Monitoring/Controlling, and Closing projects based on Microsoft Project 2019 features and functionalities
3. The Wiki should be supported by related materials sourced from trusted public domain resources and academic journals.
4. The word length of this Wiki project (information on two PMS) will be no more than 4,500 words.
Non-functional requirements
The Wiki should be easy to read and understand (high quality- usability).
Copy and paste the above in your scope statement document and fill in the rest of the sections

## Slide 17: Examples of high-level requirements
Functional requirements- features of a system. Example:
R1. The Background Task Manager shall display status messages in a designated area of the user interface at intervals of 60 seconds.
R2. If background task processing is progressing normally, the percentage of the background task processing that has been completed shall be displayed.
R3. A message shall be displayed when the background task is completed. R4. An error message shall be displayed if the background task has stalled.
Shall, Will, and Should is the standard requirements terminology

## Slide 18: Non-functional requirements
Non-functional requirements:
  are the quality attributes such as reliability, performance, security, usability, and compatibility.
  Not a "feature" of the system, but are a required characteristic for success
Example:
R1 The System shall have an availability of 999/1000 (or 99.9%).
  reliability requirement (out of every 1000 requests, 999 must be satisfied).
R2 The System shall process a minimum of 8 transactions per second.
a performance requirement
R3 The access permissions for system data will only be changed by the system’s data administrator
R4 All system data should be backed up every 24 hours and the backup copies stored in a secure location
which is not in the same building as the system
R5 All external communications between the system’s data server and clients shall be encrypted
3, 4 & 5 security requirements

## Slide 19: Non-functional requirements
R6 Novice users shall perform task X in Y minutes.
R7 The system shall use the screen pictures shown in App. xx.
R8 The menu points and push buttons shall function as shown in App. yy. R9 The system shall follow the MS-Windows style guide.
R10 For input fields with a limited set of values, it should be possible for the user to select the value from
a list.
R11 The interface should resemble the interface of application xx.
6-11 usability requirements

## Slide 20: Work Breakdown Structure (WBS)
WBS provides projects with phases and tasks or work items (i.e., project lifecycle) and enables us to define the PM methodology
  is a deliverable-oriented grouping of the work
  must enable to deliver the scope of a project captured in the scope statement document.
WBS provides the basis for planning a project schedule, and budget (cost), including executing, M/C & closing a project
WBS must enable:
  Decomposition - subdividing project deliverables into smaller pieces
  A work package is a task or work item at the lowest level of the WBS
WBS must capture the entire PM methodology- (PMI provides the planning phase + development method to give the other phases in the project)
For assignment 1 the WBS will come from PMI (planning) + SDLC method

## Slide 21: Work Breakdown Structure (WBS) based on SDLC method
WBS—SDLC (Systems Life Cycle Method) follows a systematic approach with the following phases: planning, analysis, design, implementation, and deployment (support and security).
1. Planning phase- (Initiating and planning based on PMI PM tasks)
Initiate the project (PMI)
Evaluate the business case (preliminary investigation report)
Develop all the needed plans (PMI based)
Verify plans (M/C PM task)
Phase deliverable is the project proposal (list of plans)- closing PMI task
2. Analysis phase (Executing, and Monitoring and Controlling based on PMI PM tasks)
Gathering the requirements- interviews, document reviews, observation, surveys, research, brainstorming
Verify requirements (M/C PM task)
Create analysis models- data flow diagrams (DFD), context diagram, Lower-level DFDs
Verify analysis models (M/C PM task)
Phase deliverables are the analysis models with the requirements document- Closing PMI PM task
3. Design Phase (Executing, and Monitoring and Control based on PMI PM tasks)
Interface design
Design models
Data design
Systems architecture design
Verify all design models (M/C PM task)
Phase deliverables are the interface design, design models with the analysis models & requirements document- Closing PMI PM task

## Slide 22: Work Breakdown Structure (WBS) based on SDLC method
4. Implementation (development and testing)- Execute and Monitor and Control based on PMI PM task
Code/develop
Testing (validation) (M/C PM task)
Documentation
Phase deliverable is implemented system with documentation)- closing PMI PM task
5. Deployment phase (Executing, and Monitoring and Control based on PMI)
Installation
Systems changeover and sign-off (M/C PM task)
Phase deliverable is a fully functional system in an operational environment- closing PMI PM task

## Slide 23: Work Breakdown Structure (WBS)
Use the WBS based on SDLC as a model to create the project phases and tasks (PM methodology) for assignment 1. This will be used to plan the schedule, develop a budget plan, create a quality assurance plan, milestone report, etc.
Adapted for the wiki assignment based on the SDLC method
Planning phase
1.1 Project initiation
1.1.1 Stakeholder register
1.1.2 Project charter
1.1.3 Business case
      1.2 Develop project plans
      1.2.1 Stakeholder management strategy document
      1.2.2 Risk register
      1.2.3 issue register
      Part 1 milestone
      1.2. 6 Communications management plan & communication stakeholder register
      1.2.7 Change management plan
      1.2.8 Scope statement
      1.2.9 Work Breakdown Structure (WBS)

## Slide 24: Work Breakdown Structure (WBS)
1.2.10 Project Schedule
      1.2.11 Risk Register (version 2)
      1.2.12 Issue register (version 2)
      1.2. 13 Milestone report (version 2)
      1.2. 14 Quality assurance plan
      Part 2 milestone
      Planning phase deliverable- (Part 1 and Part 2 plans). These plans must be approved and then only the next phase can begin
2. Analysis phases (the work that will be done based on the execution of the scope statement document & schedule etc.)
2.1 Requirements gathering
2.1.2 Research on PM Software Selection Criteria
2.1.2.1 Library research on PM software selection criteria
2.1.2.2 Web research on PM Software selection criteria
2.1.2.3 Compile the selection criteria
2.1.2.4 Product manager & product owner feedback on the selection criteria (M/C task)
2.1.2.5 Improvement based on the feedback on the selection criteria (M/C task)
2.1.3 Investigate Microsoft (MS) Project 2019
2.1.3.1 investigate MS project features (initiating & planning) in the lab relating to five process groups (two sub-tasks)
2.1.3.2 investigate MS project features (executing, M/C, and closing) to five process groups (two sub-tasks)

## Slide 25: Work Breakdown Structure (WBS)
2.1.3.3 Compile the MS project features in relation to five process group
2.1.3.4 Product manager & product owner feedback on the MS project features
2.1.3.5 Improvement based on the feedback on the MS project features
2.1.4 PM Software selection
2.1.4.1 Google PM Software Products to Identify the 4 major ones (pick 4 from the top of your search)
2.1.4.2 Product manager & product owner feedback on the selected 4
2.1.4.3 Improvement based on the feedback on the 4 PM software
2.1.5 investigation of the 4 PMS based on the selection criteria
2.1.5.1 Apply and compile information on the 4 PM software based on the selection criteria (you can break this into sub-tasks)
2.1.5.2 Product manager & product owner feedback on 4 PM software based on gathered information on each
2.1.5.3 Improvement based on the feedback on the 4 PM software (M/C task)
2.1.5.4 Product manager & product owner to choose the two PM software
2.1.6 Compile information on two selected PM software based on MS Project features
2.1.6.1 Apply MS project features to compile information on selected PM software 1
2.1.6.2 Apply MS project features to compile information on selected PM software 2
2.1.6.3 Product manager & product owner feedback on the information complied on 2 PM software
2.1.5.4 Improvement based on the product manager and product feedback on the 2 PM software

## Slide 26: Work Breakdown Structure (WBS)
2.1.7 Research on wiki design
2.1.7.1 Research to identify 3 wiki design
2.1.7.2 Feedback on 3 wiki design by the product manager and product owner
2.1.7.3 Improvement (pick another decision) based on the feedback
2.1.7.4 Product manager and product owner to choose 2 wiki design
Analysis phase deliverables- requirements document (outputs or deliverables of each major task in the analysis phase)(M/C)
3. Design phase
3.1 Create a prototype based on Wiki design 1 and information compiled in the analysis phase
3.2 Create a prototype based on Wiki design 2 and information compiled in the analysis phase
3.3 Product manager and product owner feedback on prototypes
3.4 Prototype improvements based on the feedback
3.5 Prototype selection by the product manager and product manager for wiki implementation
Deliverable- requirements documents and wiki design for implementation (M/C)
4. Development (Implementation) phase
4.1 Cut and paste the selection criteria on the wiki (with the selected wiki design)
4.2 Cut and paste the chosen prototype and any other related information on 2 PM software on the wiki
4.3 Identify references and provide links to references on the wiki
4. 4 Do a word count (maximum 4500)
4.5 Feedback on the wiki by the product manager and product owner
4. 6 Improvements based on the feedback
5. Testing phase
6. Deployment phase

## Slide 27: Work Breakdown Structure (WBS)
5. Testing (implementation) phase
5.1 Usability testing with R&D students
5.2 Improvements based on the usability testing
5.3 Write documentation
5.4 Write a lesson learnt report
Deliverable- wiki, plans & documents and lesson learnt report(M/C)
6. Deployment phase
6.1 Deploy the wiki
6.2 Handover/sign off.
Deliverable- wiki up and running
Copy and paste the above Work Breakdown Structure in your WBS document

## Slide 28: Advice for Creating a WBS
A unit of work or work package should appear at only one place in the WBS.
The work content of a WBS item is the sum of the WBS items below it
A WBS item is the responsibility of only one individual, even though many people
maybe working on it
The WBS must be consistent with the way in which work is actually going to be performed; it should serve the project team first, and other purposes only if practical

## Slide 29: Monitoring and Controlling: Validating Scope
It is very difficult to create a good scope statement and WBS for a project
It is even more difficult to verify project scope and minimize scope changes
Scope validation involves formal acceptance of the completed project deliverables
Acceptance is often achieved by a customer inspection and then sign- off on key deliverables

## Slide 30: Monitoring and Controlling Scope
Scope control involves testing (producing various metrics - bug reports) and controlling changes to the project scope
Formal testing (unit, integration, systems & usability testing) and testing by customer (acceptance testing) validate the scope
In assignment one, testing is done throughout- feedback by Product manager/product owner and usability testing
Goals of scope control are to:
  assure changes are processed according to procedures developed as part of integrated change control, and
  manage changes when they occur; need to have the following
    Change Management Plan (see the template)
    Change Request Form (see the template)

## Slide 31: Summary
Project scope management includes the processes required to ensure that the project addresses all the work required, and only the work required, to complete the project successfully
Main processes include
  Define scope management
  Collect requirements
  Define scope
  Creating the Work Breakdown Structure
  Validate scope
  Control scope

## Slide 32: Homework
Continue to work on Assignment 1
This week’s reading is Chapter 5 from Information Technology Project Management (2019) by Kathy Schwalbe
Next week- Schedule Management